UNDP Project Document

Government of Kenya

United Nations Development Programme

World Bank

PIMS 3792, Kenya: Adapting to Climate Change in Arid and Semi-Arid Lands (KACCAL)

Period covered: 2009-2013

Brief description

According to Kenya’s First National Communication (2002), the incidence of droughts is anticipated to increase both in intensity and frequency as a result of climate change.  In response, UNDP and the World Bank have initiated a joint project on Adaptation to Climate Change in Arid and Semi-Arid Lands (KACCAL) aimed at facilitating adaptation of the key stakeholders in arid and semi-arid lands to long-term climate change.  The joint project seeks to develop and pilot a range of coping mechanisms for reducing the vulnerability of small-holder farmers and pastoralists in rural Kenya to long-term climate change, including variability.  The project is funded through the Special Climate Change Fund, with the World Bank managing US$ 5.5 million and UNDP entrusted with overseeing US$ 1million.

This Project Document focuses on the UNDP-managed component of the joint UNDP-World Bank KACCAL project.  Project activities are aligned with UNDP’s comparative advantage in aspects of capacity building, and support for MDG-based planning, as well as experience in designing and implementing climate change adaptation and sustainable land management projects.  The UNDP component focuses primarily on enhancing adaptive capacity of key stakeholders in the District of Mwingi, complementing the support given by the World Bank in four other districts: Garissa, Turkana, Marsabit and Malindi.

Table of Contents

Section											    Page

Acronyms

PART I: Situation Analysis

SECTION I: ELABORATION OF THE NARRATIVE

Context and Global Significance

Baseline analysis

Sustainable livelihoods

Climate risk integrated across sectors, community services and programmes

PART II:  Strategy

Project Rationale and Policy Conformity

Project Goal, Objective, Outcomes and Outputs/activities

Project Indicators, Risks and Assumptions

Country Ownership: Country Eligibility and Country Drivenness

Sustainability

Replicability

PART III: Management Arrangements

PART IV: Monitoring and Evaluation Plan

PART V: Legal Context

SECTION II: LOGFRAME

SECTION III: Total Budget and Workplan

PART I: Other agreements

SECTION IV: ADDITIONAL INFORMATION

PART IV: Stakeholder Involvement Plan

PART V to X: Other additional information

Annexes

Annex 1: Terms of References (TORs)

Annex 2: Terms of Reference for the Regional Component of the UNDP Coping with Drought and Climate Change Project in Kenya, Ethiopia, Zimbabwe and Mozambique

Annex 3: Stakeholder Involvement Plan

Annex 4: UNDP Template for lessons learned in adaptation projects

Annex 5: Minutes from CwD Project Stakeholders’ Workshop

Annex 6: Maps

Annex 7: Photographs of UNDP pilot sites

SIGNATURE PAGE

# Acronyms

AAK		Action Aid Kenya

AEZ	Agro-Ecological Zones

ALM	Adaptation Learning Mechanism

ALRMP 	Arid Lands Resource Management Project

APF	Adaptation Policy Framework

APR	Annual Project Report

ASAL	Arid and Semi-Arid Lands

AWP	Annual Work Plan

CBO	Community Based Organization

CBS	Central Bureau of Statistics

DDC	Dryland Development Center

DMP	Desert Margins Programme

ERS	Economic Recovery Strategy for Wealth and Employment Creation

EW	Early Warning

FAO	Food and Agriculture Organization of the United Nations

FEWS-NET	Famine Early Warning System-Network

FFS 	Farmer Field Schools

FNPP	FAO Netherlands Partnership Programme

GDP	Gross Development Product

GEF	Global Environment Facility

GoK 	Government of Kenya

IA	Implementing Agency

ICPAC	IGAD Climate Prediction and Application Centre

IPM	Integrated Pest Management

IPPM	Integrated Production and Pest Management

ITCZ	Inter-Tropical Convergence Zone

KAPP	Kenya Agricultural Productivity Project

KARI	Kenya Agricultural Research Institution

KMD	Kenya Meteorological Department

MoA	Ministry of Agriculture

MoLF	Ministry of Livestock and Fisheries

NC	National Consultant

NCPB	National Cereals and Produce Board

LADA	Land Degradation Assessment (A GEF – UNEP project via FAO)

LUCID	Land Use Change in Development (A GEF – UNEP project)

NALEP	National Agriculture and Livestock Extension Programme

NAP	National Action Programme to Combat Desertification and Drought

NCSA	National Capacity Self Assessment

NEMA	National Environment Management Authority

NGO	Non-Governmental Organization

PDF B	Project Development Phase

PFI	Promoting Farmer Initiatives

PIR	Project Implementation Review

PRSP	Poverty Reduction Strategy Programme

RANET	Radio Network

RCU	Regional Coordinating Unit

SIDA	Swedish International Development Aid

SLM	Sustainable Land Management

SPFS	Special Programme for Food Security

SPA	Strategic Priority on Adaptation

SRA	Strategy for Revitalization of Agriculture

TPR	Tripartite Review

TTR	Terminal Tripartite Review

UN	United Nations

UNDP	United Nations Development Programme

UNEP	United Nations Environment Programme

WB	World Bank

# SECTION I: ELABORATION OF THE NARRATIVE

# PART I: Situation Analysis

1.  Kenya’s geographic location makes it inherently prone to cyclical droughts and floods.  However, according to the First National Communication (INC), such types of cyclical climate-driven events will increase in intensity and frequency due to global climate change.  Serious repercussions are anticipated thereby not only on agricultural productivity but also the achievement of poverty reduction and other Millennium Development Goals.  In response, UNDP and the World Bank, with funding from the Special Climate Change Fund through Global Environment Facility (GEF), have designed a four-year (2008-2012) project for implementation entitled “Adaptation to Climate Change in Arid and Semi-Arid Lands” (KACCAL).  The project seeks to facilitate adaptation of key national and local level stakeholders to long-term climate change by developing capacity to manage climate risks, adjusting relevant national policies and programmes to better reflect impending concerns, and piloting a range of priority coping mechanisms for reducing vulnerability of small-holder farmers and pastoralists in rural Kenya.  In November 2006, GEF Council subsequently approved US$ 6.5 million for the KACCAL project, with the World Bank entrusted to manage US$ 5.5 million and UNDP to oversee US$ 1 million.  The project builds on an existing development baseline in Kenya (largely activities led by the Arid Lands Resource Management Programme and the Ministry of Agriculture), with SCCF resources earmarked for specific activities that increase adaptive capacity to cope with droughts and floods under changing long-term climate conditions.

2.  This project document is for the UNDP managed activities of the KACCAL project.  Activities focus primarily (although not exclusively) on interventions in the Mwingi district.  The district, which is in the semi-arid Ukambani region, has a 66% chance of climate induced-crop failure each year.  The UNDP component is anchored around three global level outcomes which underpin the joint UNDP/World Bank KACCAL project:

- strengthened knowledge base, coordination and information sharing towards action on management of climatic risk at the National and Regional levels,

- capacity developed and investments made to integrate CRM into local/district planning, and for engaging the private sector, and

- Support for community driven initiatives to enhance the resilience of livelihoods and ecosystems to climatic risk.

3.  UNDP-led activities will enhance adaptive capacity in this pilot area in terms of (a) strengthening drought mitigation skills of extension workers whose role is to support household and community based projects; (b) improve the flow and use of early warning information in drought/flood mitigation practices in community services and programmes; and (c) identify and remove barriers impeding adaptive capacity of community level stakeholders to overcome long-term climate change risks.  The World Bank’s activities will focus on interventions in another four districts within Kenya.

4.  The design of UNDP’s planned interventions within the KACCAL project has been guided by UNDP’s Adaptation Policy Framework (APF) approach in that it took into consideration current vulnerabilities (to climate and non-climatic factors), future climate change and anticipated risks, and adaptive capacity requirements and barriers.  The project design phase benefited from a participatory approach where stakeholders from government, communities, donors and other interested parties were consulted and had the opportunity to contribute.

# Context and Global Significance

National environmental context: Location

5.  Kenya has a total area of approximately 82 400 km2, and lies on the eastern coast of Africa with the equator bisecting the country.  The altitude varies from sea level to about 5000 meters above sea level in the central highland regions.  Lakes occupy about 2% of total area, 18% of the land area is considered high production agricultural land, and arid and semi-arid lands (ASALs) occupy the rest of the country.

Climate characteristics

6.  Annual rainfall follows a strong bimodal seasonal pattern.  Generally, the long rains occur in March - May, while the short rains occur in October – December, but with variations.  Distribution of rainfall is influenced by topography.  The country's climate is influenced by its equatorial location, topography, the Indian Ocean, and the inter-tropical convergence zone (ITCZ).  The influence of the ITCZ is modified by the altitudinal differences, giving rise to varied climatic regimes.  Kenya has seven agro-climatic zones (Figure 1.1 and Table 1.1).  Rainfall varies from over 2000mm in the humid to less than 300mm annually in the very arid zones.

Figure 1.1 Agro-climatic Zones of Kenya

Table 1.1 Agro-climatic Zones of Kenya

| Zone | Climatic Zones | Mean Annual Rainfall | % Of Total Land Area |
| --- | --- | --- | --- |
| I | Humid | 1,400 - 2,700 | 3 |
| II | Sub – Humid | 1,000 - 1,600 | 4 |
| III | Semi – Humid | 800 - 1,400 | 5 |
| IV | Medium to Semi Arid | 600 - 700 | 5 |
| V | Semi Arid | 500 - 600 | 15 |
| VI | Arid | 300 - 550 | 22 |
| VII | Very Arid | < 300 | 46 |

Source: NEAP (1994)

Water

7.  The major drainage systems in Kenya include the Lake Victoria, Rift Valley, Athi, Tana, Ewaso Nyiro, and North-Eastern basins.  As drainage is influenced by the country's topography, the main rivers drain from the central highlands into the Rift Valley and eastwards into the Indian Ocean and westwards into Lake Victoria.  Rivers in the north (including from Mount Elgon and from the highlands along the Sudan-Ethiopian border) drain mainly into Lake Turkana.

8.  Although Kenya has numerous rivers, a comparatively small number are permanent.  They include the Tana, Athi, Nzoia, Yala, Sondu, Nyando and Mara rivers.  Several of the rivers have been dammed upstream to provide hydroelectric power, irrigation water, and water for domestic use.

Soils

9.  Kenya is a country with varying climate, vegetation, topography, and underlying parent rock.  Climate is the most important factor influencing soil formation.  Climate affects the soil types directly through its weathering effects and indirectly as a result of its influence upon vegetation.  In most parts of Kenya, soils are deficient in nitrogen (N), phosphorous (P), and occasionally potassium (K).  In dry areas, the soils have low organic matter mainly because rainfall is low, variable, unreliable, and unevenly distributed.

Socio-economic conditions

10.  Kenya has a population estimated at 32.4 million (2004), of which over 80% live in rural areas and significantly depend on the exploitation of land and its natural resources for their sustenance.  The gains made in reducing population growth from over 3.0% in the 1970s and 1980s to around 1.8% in early 2000s, and improved life expectancy of 60 years due to improved medical infrastructure has been set back by the HIV/AIDS pandemic which has reduced life expectancy to only 45 years.

11.  The ASAL areas cover 48 million hectares, of which 9.6 million hectares supports some type of agriculture, almost 15 million hectares are only suitable for largely sedentary livestock production and the remaining 24 million hectares are dry and only suitable for nomadic pastoralism (NEMA, 2003).  ASAL areas in Kenya are home to about 30% (about 10 million) of human and 50% of livestock populations respectively, and are habitat to about 75% of wildlife, the backbone of Kenya’s tourism sector.  Population has also significantly increased in Kenya undermining the coping ability of most communities, particularly in the ASAL areas hence rendering people more vulnerable.  The recurrence and intensity of droughts has increased in Kenya, particularly affecting ASAL areas, which now experience droughts almost on an annual basis.

Agriculture

12.  Kenya’s economy depends largely on its natural resources through agriculture, livestock production, fisheries, forestry, tourism and agro-based industries (UNEP & GoK, 2000).  Agriculture is the main economic sector contributing 16.6% of the Gross Domestic Product (GDP).  Of the 53% economically active population, approximately 74% is employed in agriculture.  About 80% of all people working in agriculture are smallholders.  The country often has food deficits as a result of periodic droughts and low access to production resources.  In the ASALs, about 2 million people are permanently on famine relief and the number sometimes rises to 5 million during severe droughts.  Despite 80% of the country being ASAL, agriculture in Kenya is predominantly rain-fed making it highly vulnerable to climate change.  Livestock production plays a major role in food security and in the economy of the country since it sustains the livelihood of the population living in the ASALs.

Vulnerability to Climate Change

13.  Kenya is prone to cyclical droughts with major ones occurring every ten years and minor ones every three to four years (UNEP and GoK, 2000, Downing, T., E.  et al, 1989).  It is expected that increase in intensity and frequency of droughts, that are projected with climate change will enhance the adverse impacts of droughts.  The following section discusses results of climate change studies in Kenya and current and future impacts on some key sectors of the economy.

Climate change scenarios

14.  In the Initial National Communication (INC) of Kenya, General Circulation Models (GCM) used to develop climate change scenarios indicated increasing temperature changes at all locations with doubling of carbon dioxide.  Increases varied significantly not only from month to month, but also from location to location.  The increases ranged from 0.5 to 3°C.  Two GCMs namely, CCCM and GFDL3 were found to give reasonable results for the various locations in Kenya.  Both models indicated increasing temperature trend with a maximum of about 3°C with the doubling of CO2.

15.  GCM-based future annual rainfall scenarios over Kenya for the year 2030 using the Canadian Climate Center Model (CCCM) is shown in figure 5.4(c).  The GCM-based annual and seasonal rainfall scenarios seem to be controlled more strongly by large-scale mean earth-atmosphere-oceans causative factors.

16.  The annual GCM rainfall projections show that the region extending from Lake Victoria to the central highlands east of the Rift Valley will experience mild increases in the annual rainfall.  The remainder of the country is expected to receive reduced annual rainfall amounts.

17.  The spatial distribution patterns of the relative adjustments of the mean annual rainfall indicate that only a few areas in the country will experience positive adjustments.  Such areas are found in the vicinity of the City of Nairobi only.  All other parts of the country will experience negative mean annual rainfall adjustments with the lowest relative adjustments found in central and northwestern parts of Kenya.

18.  The following socio economic sectors were identified to be highly vulnerable in Kenya’s Initial NC:

- Agricultural sector

- Water resources

- Aquatic and coastal resources: inland and marine water fisheries including the coastal zone related to level use

- Human health; malaria, African trypanosomiasis and cholera

- Terrestrial ecosystem; forestry and rangelands

Agriculture sector

19.  The overall adverse impacts of the extreme weather and climate events that could occur because of the projected climate change in Kenya would be associated with mass migration, food shortages, water, energy, famine, shortage of essential basic commodities, loss of life and property together with many other socio-economic disasters.  It is therefore apparent that the space-time variability of rainfall could have far reaching socio-economic impacts in Kenya.

20.  The two extreme climate events that would adversely impact on the agricultural sector are drought, which would result in crop water stress and hence yield reduction, and flooding resulting in water logging in both the ASALs and high potential areas.  This will lead to reduction in crop yields and shortage of forage, increased disease incidences for both human and livestock, as well as breakdown of marketing infrastructure.  Other more direct negative impacts include habitat modification, ecosystem degradation, losses in biodiversity, accelerated desertification, and increase in the occurrence of other related natural disasters.

Figure 1.2: GCM-based annual rainfall scenarios for the year 2030, expressed as percent increment of the annual rainfall above/below the 1990 baseline values

Water resources

21.  Kenya has a wide spectrum of the water resources base, which consists of both surface and groundwater resources (fossil and rechargeable).  The terrestrial-surface-water resources systems are strongly influenced by rainfall.  Most projections of future climate change in Kenya indicate that rainfall will either increase or remain unchanged in the humid areas, but will decrease in the arid and semi-arid areas.  All these imply that, terrestrial surface water resources are very vulnerable to the impacts of climate change.

Policy, legislative and institutional context

22.  Among the recent initiatives are the National Environment Action Plan of 1994; Session Paper no.  1 of 1994 on Recovery and Sustainable Development by the Year 2010; the National Poverty Eradication Plan (1999), and Poverty Reduction Strategy Paper (2001), while the latest initiative is the Economic Recovery Strategy for Wealth and Employment Creation (2003) that dedicated two of its chapters to ASALs.  A common constraint faced by for many of these previous programmes and policies is the lack of commitment and coordination between line ministries.

23.  The review of the ASAL Development Policy and Investment Plan (dating from 1992) is a recent activity, relying on participatory national and localized stakeholder discussions and drafting sessions.  The draft revised policy documents indicate the past decades of gaps and political failures regarding the necessary attention to Kenyan ASALs, which is of key importance to understanding the situation and development state of Kenyan ASALs.  The policy presents a new approach to development in the ASALs as it introduces an integrated cross-sectoral approach to sustainable development and links this to an investment plan for all relevant sectors.  The investment plan was prepared by each of the line ministries and the two coordinating ministries.

24.  In March 2004 the Ministry of Agriculture launched the Strategy for Revitalization of Agriculture (SRA), which gives special attention to the ASALs and agro-pastoralists.  The SRA stresses the need for developing a participatory extension system that is responsive to the needs of the communities in the ASALs.  The Economic Recovery Strategy for Wealth and Employment Creation (ERS) gives particular emphasis to agriculture as the engine for growth for the Kenyan economy (Ministry of Agriculture, March 2004).  The overall goal is to achieve a progressive reduction in unemployment and reduce the level of poverty.

25. The Draft National Land Policy of May 2007 notes the need to ensure that land use and practices under pastoral tenure in ASALs conform to principles of sustainable resource management and that disaster management legal and policy frameworks for prevention and management of land related disasters will be ensured. The First Medium Term Plan (2008-212) of Vision 2030: Chapter 5 notes that climate change is a serious challenge to Kenya’s economic development due to low adaptive capacity.

Stakeholder analysis

26.  The design of this project relied on extensive stakeholder consultations during the design phase.  Once pilot sites had been identified based on vulnerability assessments, stakeholder consultations were undertaken with the local communities to identify which adaptation measures are relevant in specific sites.  Participatory Rural Appraisal approaches were used to validate the community’s vulnerability profile and ascertain demand for specific interventions.  Other secondary data sources, including consultations with local and international expertise on climate change risk management were used to validate the findings.

27.  The National Communications provided a useful reference point for discussions on priority interventions at stakeholder consultations but the scale of analysis demanded that further work be done at a micro-scale level to better appreciate underlying barriers and opportunities.  This was necessary given that local communities in the pilot region were not only the primary beneficiaries of the project, but also key partners.

28.  During formulation of the UNDP component both informal and formal consultations were held with representatives from the Ministry of Agriculture, Ministry of Livestock and Fisheries Development, Ministry of Water Development, National Environment Management Authority and UNFCCC Focal Point, University of Nairobi, Kenyatta University, Kenya Forestry Research Institute, Arid Lands Resource Management Authority, FAO Kenya, Kenya Meteorological Department, ICPAC, and various NGOs and CBOs and also representatives of farmers and pastoralists in Mwingi District (Annex 6).  Formal consultations were held through two national stakeholder meetings at the Ministry of Agriculture Headquarters and a stakeholder workshop held at Mwingi District Headquarters.

29.  Key stakeholders in the implementation of this project are listed in Table below.

Table 1.2:   Stakeholders and their Roles

| Organization | Role | Technical Input |
| --- | --- | --- |
| Ministry of Agriculture | Participation in the Project Board Provision of extension support to communities District level Agricultural Policy & Management | Land use planning, soil and water conservation, agricultural training and extension Policy formulation |
| UNDP CO | Accountability to GEF for funds disbursement for overall delivery of project results; Member of Project Board | Ensure project implementation adheres to guidelines of the SPA and also alignment with UNDP’s Adaptation Portfolio |
| Ministry of Environment and Natural resources | Environmental Policy | Policy formulation Integrating climate change risk management into Environment Policy Driving the integration of climate change risk management into operations of other line Ministries |
| National Environmental Management Authority | Environmental Impact assessment | Environmental management; Coordination with other national initiatives on climate change adaptation |
| Arid Lands Resource Management Programme (ALRMP) | Project Management Services | Vulnerability and Food security Assessments Coordination with World Bank Component |
| Ministry of Water Development | Technical support on water resources management | Catchment management |
| Kenya Meteorological Department | Provision of climatic information | Weather stations, climate monitoring and forecasting |
| IGAD Climate Prediction Application and Centre (ICPAC) | Provision of climate seasonal predictions and early warning | Climate modeling Training for local communities |
| Ministry of Livestock and Fisheries Development | Technical support for livestock development | Livestock production |
| Forestry Department | Information on land use planning | Land use planning Forest management |
| Mwingi District Development Committee | Facilitating involvement of community leadership | Coordination of socio-economic development |
| Development Partners | Co-financing |  |
| NGOs and CBOs | Livelihoods training Community facilitation Co-financing | Resource mobilization Community facilitation |
| Local Communities | Community project implementation Input in adaptation project design | Monitoring of results |
| Universities | Livelihood research and training | Research and training |

# Baseline analysis

Drought impacts

30.  Over 70% of the natural disasters in Kenya are related to extreme weather and climate events such as strong winds, droughts, and floods amongst others.  Extreme weather and climate events influence the entire economy of the country with droughts and floods having the highest adverse effects on the economy.  The majority of the major shortfalls in food supply recorded in 1928, 1933-34, 1937, 1939, 1942-44, 1947, 1951, 1952-55, 1957/58, 1984/85 and 1999-2000 could be easily associated with rainfall deficits experienced in the respective years.  The timing, intensity, duration and total magnitude of the rains are the key factors in the maize harvest (which is the major food crop), with the long rains (March-May) playing the most important role.  Some of the recent droughts include the 1983/84 and 1999/2000 and the current 2005/2006, which is ravaging the country, especially in the ASALs.  The earlier two droughts had wide-spread social and economic impacts and the current one is proving no different.  The 1999-2000 drought was amongst the longest and severest droughts on record in Kenya.  Some recent floods include 1961/62 and 1997/98.  The 1997/98 floods were amongst the most intense and widespread on record.

31.  Droughts are the most common disasters affecting Kenya.  Kenya has recorded 28 major droughts in the last 100 years, three of them occurring during in the last decade.  The severity and frequency of droughts in the country seem to have increased over time.  Some of the droughts that have occurred in Kenya include the 1952 – 1955, 1973 – 1974, 1983 – 1984, 1992 – 1993, and 1998 – 2000 droughts.  Detailed analysis of these droughts is shown in Table 1 below.  The 1999/2000 drought was widespread and affected northern, central, eastern, and coastal parts of Kenya while the Drought in 2003/2004 affected parts of northern, eastern, and coastal areas of Kenya.  These droughts resulted in energy crisis, food, and water shortages with the pastoral communities in the ASALs being the hardest hit.  One on the districts within the ASALs that has experienced severe drought impacts is Mwingi, in the Northeastern Province of Kenya.  Table 1.3 shows the history of droughts occurrence in Kenya.

Table 1.3: History of drought occurrences in Kenya

| Period | Areas affected | Remarks |
| --- | --- | --- |
| 1883 | Coast | Worst famine in 30 years |
| 1889 – 1890 | Coast | One year of drought and famine |
| 1894 – 1895 | Coast | Information not available |
| 1896 – 1900 | Countrywide | Failure of three consecutive rainy seasons. Human deaths reported |
| 1907 – 1911 | Lake Victoria, Machakos, Kitui and Coastal | Minor food shortages |
| 1913 – 1919 | Eastern and Coastal Provinces | Impacts exacerbated by war |
| 1921 | Coastal | A record dry year at the coast |
| 1925 | Rift Valley, Central and Coastal Provinces | Local food shortages, crop and livestock losses |
| 1938 – 1939 | Northern, Rift Valley and Central Provinces | Heavy loss of livestock, Lorian Swamp dried up; deaths occurred |
| 1942 – 1944 | Countrywide | Food shortages, human deaths reported |
| 1947 – 1950 | Central and Coastal Provinces | Very severe drought in Coast Province |
| 1952 – 1955 | Eastern, Central, Coast, Nyanza, Western and Rift Valley Provinces | Water shortages |
| 1960 – 1961 | Eastern, South/North Rift Valley | High cattle mortality |
| 1972 | Widespread | Water shortages, wildlife deaths |
| 1973 – 1974 | Most of Kenya | Human and livestock deaths |
| 1974 – 1976 | Northern, Central and Eastern Provinces | Heavy livestock losses |
| 1980 | Central, Eastern, Western and Coast Provinces | Paralysed crop production, water shortages |
| 1981 | Eastern Province | Famine |
| 1983 | Countrywide | Water shortages, human and livestock migration |
| 1984 | Central, Rift Valley, Eastern, North Eastern | Large food deficits |
| 1987 | Eastern and Central | Severe food shortages |
| 1992 – 1994 | Northern, Central and Eastern Provinces | Moderate food shortages |
| 1999 – 2000 | Countrywide except west and coastal belt | Shortage of food supply, heavy reliance on relief food, shortages of supply, interruption of electricity supply |

Source: UNEP & GoK: Devastating Drought in Kenya: Environmental Impacts and Responses

Early warning systems

32.  The various organizations/institutions in Kenya that are involved in data collection for early warning systems include Kenya Meteorological Department (KMD), Ministry of Agriculture, Department of Resource Survey and Remote Sensing (DRSRS), IGAD Climate Prediction and Application Centre (ICPAC), Kenya National Bureau of Statistics (KNBS), National Cereals and Produce Board (NCPB), Famine Early Warning System-Network (FEWS-NET) and Arid Lands Resource Management Project (ALRMP), World Food Programme (Vulnerability assessment Mapping) Kenya Office, Livelihood Early Warning Systems (LEWIS), Livestock Network and Knowledge System ( LINK), Regional Center for Mapping of Resources for Development (RCMRD).

33.  The KMD provides climate monitoring and prediction services.  It works in collaboration with the IGAD Climate Prediction and Application Centre and other International Climate Prediction Centers the Department issues probabilistic seasonal climate forecasts derived from a blend of statistical and global circulation models.  Since 1997 climate experts and users have regularly convened twice per year at the IGAD Regional Climate Outlook Forum (COF) to produce a consensus forecast for the IGAD region, which in turn is downscaled by the respective National Meteorological Services for national consumption.  The print and electronic media have been the main dissemination channels for seasonal climate forecast information.

34.  Although climate and early warning information could be available at the district headquarters, there is inadequate extension service to disseminate this information to the end users.  In most cases there is lack of competent personnel to interpret the information to a user-friendly format.  The KMD whose mandate it is to provide free weather and climate information has also in the last decade commercialized some of its services.  For example a ten-day agro meteorological bulletin, which used to be issued free to the farming community, is no longer available.  Specialized agrometeorological analysis is now only available on demand and at a fee.

Food security situation

35.  Food availability at household level in the ASAL districts, which include Mwingi, has been declining lately due to crop failure in the last four consecutive seasons.  The main constraints to food insecurity in the district are lack of water for human consumption and agriculture, and lack of employment opportunities.  Table 1.4 below shows seasonal yields of the main crops grown in the district.

Table 1.4: Five Year Seasonal Crop Yields (Tons/Ha) for Major Crops Grown in Mwingi District

| Crop Type | Crop Yield (Tonnes/Ha) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1999 |  | 2000 |  | 2001 |  | 2002 |  | 2003 |  |
|  | Long Rains | Short Rains | Long Rains | Short Rains | Long Rains | Short Rains | Long Rains | Short Rains | Long Rains | Short Rains |
| Beans | 0.072 | 0.360 | 0.000 | 0.095 | 0.000 | 0.630 | 0.179 | 0.900 | 0.073 | 0.324 |
| Sorghum | 0.016 | 0.270 | 0.000 | 0.404 | 0.035 | 0.675 | 0.270 | 0.720 | 0.450 | 0.540 |
| Millet | 0.045 | 0.360 | 0.000 | 0.360 | 0.042 | 0.076 | 0.360 | 0.720 | 0.216 | 0.360 |
| Cow peas | 0.045 | 0.360 | 0.000 | 0.384 | 0.042 | 0.555 | 0.284 | 0.770 | 0.162 | 0.324 |
| Cassava | 5.000 | 8.000 | 2.000 | 2.000 | 4.623 | 5.000 | 5.994 | 3.955 | 1.000 | 8.000 |
| Green grams | 0.036 | 0.270 | 0.000 | 0.709 | 0.028 | 2.162 | 0.243 | 0.608 | 0.162 | 0.324 |
| Pigeon Peas | 0.045 | 0.044 | 0.018 | 0.360 | 0.106 | 0.670 | 0.076 | 0.779 | 0.041 | 0.486 |
| Maize | 0.027 | 0.324 | 0.000 | 0.360 | 0.017 | 0.540 | 0.000 | 0.000 | 0.090 | 0.674 |

Source:  Ministry of Agriculture (GoK)

36.  At District Level the Government of Kenya has an integrated extension programme in Mwingi that include the National Agriculture and Livestock Extension Programme (NALEP) that plans to expand into the semi-arid districts during its second phase (NALEP Phase II).  NALEP is co-funded by the Swedish International Development Agency (SIDA) that has been involved in the Kenyan agricultural sector for several decades.  The overall goal of NALEP is to enhance the contribution of agriculture and livestock to the social and economic development and poverty alleviation.  This goal will be reached though a pluralistic, efficient, effective, and demand-driven professional national agricultural extension system.  The Kenya Agricultural Productivity Project (KAPP), funded by the World Bank, also supports participatory extension mechanisms, and links this to applied research and technology adoption.

37.  The Special Programme for Food Security (SPFS) first introduced the Farmer Field School (FFS) approach on a small-scale in Kenya in 1995 of which Kenya was one of 15 pilot countries, with an initial focus on Integrated Pest Management (IPM).  Since 1995, the FFS approach has been tested and adapted for farmer driven learning for a range of crop and livestock enterprises and has increasingly been applied as a training tool for agricultural topics in general rather than just for IPM.  In 1999, FAO’s Global IPM Facility launched an East African pilot project for FFS on Integrated Production and Pest Management (IPPM) covering three districts in Western Kenya.  With IPPM as the entry point, the FFSs have included other aspects that have a bearing on production and livelihoods in general.  Improved resource management issues as well as financial management are recognized as important components for capacity-building.

### Site selection

Process followed

38.  Based on guidance provided by UNDP’s Adaptation Policy Frameworks document, three broad based criteria were identified and used to constitute a basis for selection of pilot sites for the UNDP component of the joint project.  The criteria include vulnerability to climate change, adaptive capacity, social acceptance, and food insecurity considerations.

39.  In the inception meeting for the UNDP component of the joint project, which was held on 4th October 2005, and attended by representatives from various relevant Government Ministries, Mwingi and Makueni districts satisfied all the above criteria for selection.  It was also noted that UNDP and the ALRMP has already on-going projects in both these districts.  There is also existence of Farmer Field Schools (FFS), as well as activities led the Forest Department and ICIPE in their projects in Mwingi district.  The selection of project sites in either of these two districts was therefore possible, and a final decision was reached after the completion of field surveys by the national project development team.

40.  Together with the surveys in Mwingi District, extensive consultations and discussions were held with the District personnel of the Ministries of Agriculture and Livestock and Fisheries.  Relevant reports were reviewed, including the Government of Kenya Annual District Agricultural Production Reports and District Livestock Production Reports.  Consultations were held with officials from relevant organizations working in the area including the District Environment Officer from The National Environment Management Authority (NEMA), Drought Management Officers from the ALRMP of the OP.  Other organizations consulted were Farm-Africa and community based organizations.  During the field surveys the team visited a number of farms and farmer groups (e.g.  Farmer Field Schools, (FFSs)) and held discussions with them.

Description of selected site: Mwingi District

41.  Mwingi District is one of the thirteen districts in Eastern Province of Kenya.  It borders Kitui District to the south, Machakos District to the west, Mbeere and Meru South Districts to the North and Tana River District to the East.  The district lies between latitude 0º 03’ and 1º 12’ South and longitudes 37º 47’ degrees 38º 57’ East.  The district covers an area of 10,030.30 km² of which about 18% is cultivated while the remaining (about 82%) is used for livestock production.

42.  The district is divided into 9 divisions namely Central, Migwani, Kyuso, Mumoni, Nguni, Ngomeni, Nuu, Mui, and Tseikuru, 38 administrative locations and 127 sub locations.  Figure 2(a) (Annex 4) shows the various administrative units in the district, by division.

43.  The Agro-ecological Zones of Mwingi district (Figure 2(b), Annex 4) are shown on the basis of aerial coverage in Table 2.1.

Table 2.1: Distribution of agro-ecological Zones of Mwingi District by Area

| Agro-ecological Zone | Area (Sq. KM.) |
| --- | --- |
| UM 3-4 | 19.8 |
| UM 4 | 114.9 |
| LM 4 | 952.6 |
| LM 5 | 4,995 |
| IL 5 | 531 |
| IL 6 | 3,417 |
| TOTAL | 10,030.3 |

44.  The climate of the district is hot and dry for the greater part of the year.  The maximum mean annual temperature ranges between 26º C and 34º C.  The minimum mean annual temperatures in the district vary between 14º C and 22º C.  The district has two rainy seasons, i.e.  March – May (long rains) and October – December (short rains).  Generally, the rainfall is below 800 mm per annum for most parts of the district and is very unreliable.  There are long stretches of dry, hot seasons between August and September (immediately after the cold July), and again in January and February.  Most rivers are dry through most of the year and there is limited intensive land use.  However, in Mwingi District, the short rains are more reliable than the long rains.

45.  The district has a population of 303,828 (1999 population census) comprising 162050 females and 141778 males, and is projected to rise to 377,081 people in 2008 with a growth rate of 2.4 per cent (ALRMP, 2005).  The area has a population density of between 18 and 66 persons/km², with an average population density of 30 persons per km².  Poverty levels in Mwingi are high at over 60% of the population living below the poverty line of less than US$1 a day.

46.  Water is the major limiting factor in the district and is perceived to be the most important affecting the ability of the people to have sustainable livelihoods.  The district has only one permanent river, Tana River, with several seasonal rivers most of them draining in the Tana River (ALRMP, 2005).

47.  Mwingi district is semi-arid with bimodal rainfall pattern.  The annual average rainfall ranges between 500mm and 700mm.  The district has been under Emergency operations (EMOP) since September 2004.  It started with general food distribution.  In January 2006, 85-90% of the households were mostly relying on local markets to purchase their foodstuffs and /or on the on going food interventions.  The district has experienced poor rainfall for the last four consecutive seasons, from early 2004.  There was total crop failure for the main crop of maize, sorghum, millet, beans and peas in the 2005/2006 short rains season.  The ASAL region in Kenya covers more than 80% of the total land area.  The choice of Mwingi district for this project was arrived at after consideration of all the criteria for selection.  Mwingi district has the advantage of being relatively a new district and having a very united and responsive government district team.  There are also many stakeholders including FFSs, NGOs, CBOs and international development partners, involved in various projects in the district, and which will play complementally roles to this project (see table on Stakeholders) and contribute to its success.

48.  Two sites corresponding to two administrative divisions in Mwingi District of Eastern Province of Kenya were selected for piloting and subsequent implementation of the UNDP component of the joint project.  These are Mumoni and Kyuso divisions.

Mumoni Division

49.  Mumoni division falls within ecological zone V and is inhabited by 37,609 people (17,498 males and 20,109 females) and has a total of 6,991 households.  The division is characterized by poor distribution of water sources.  In general, distances to water points are 2 and 7 km for wet seasons and dry seasons respectively.  Poverty levels are very high in the division at over 70% of the population living below the poverty line of less than US$1 a day (worldbank.org/research/povertymaps/Kenya/ch4.2.pdf).  Poverty does increase vulnerability of the population because it erodes coping abilities.

50.  Mumoni division is one of the divisions benefiting from the Promotion of Farmer Innovation/Farmer Field Schools (PFI/FFS) and FAO/Netherlands Partnership Programmes (FNPP).  The activities involved in these programmes are water harvesting (FNPP) and promotion of farmer innovations through FFS (PFI/FFS).  The projects engaged in by the FFS range from soil and water conservation, water harvesting, income generation through keeping goats and local poultry, seed bulking and operating crop trial plots.

Kyuso Division

51.  Kyuso Division lies to the east of Muumoni division and like Muumoni also falls within agro-ecological Zone V.  It is inhabited by a total population of 34,272 people (15,728 males and 18,544 females) with a total of 6,291 households.  The distribution of water sources in the division can be described as fair to poor.  It has 6 seasonal rivers, 60 water pans/earth dams, 14 dams, one sub-surface dam, 35 shallow wells and 6 boreholes.  Distances to watering points in the division are 2 km and 8 km for wet seasons and dry seasons respectively.

52.  The division is one of those in the district that is also benefiting from the PFI/FFS and FNPP programmes and the NALEP/GOK FFS programmes.  The activities involved in these programmes are water harvesting (FNPP) and promotion of farmer innovations through FFS (PFI/FFS).  The projects being undertaken by FFS in this division include keeping of goats, beef cattle and local poultry, and growing of green grams, maize, vegetables and operation of fruit tree nurseries.

53.  Poverty levels in Kyuso are high about 50 – 60% of the population living below the poverty line.  This, however, is better than in Mumoni where the proportion of people living below the poverty line is over 70%.

### Results of Mwingi District Baseline survey

Process followed

54.  Participatory Rural Appraisal (PRA) techniques and interviews with stakeholders at the sites for the UNDP component of the joint project were used to identify and prioritize various issues.  Consultations through formal and informal discussions were carried out by the technical team with various heads of department and sections of government at the Mwingi District Headquarters.  Field excursions in the company of senior district government officials were conducted in the two divisions.  There were extensive formal and informal discussions with various farmer groups in the two selected divisions.  A qualitative assessment in the field was carried out during which meetings with target groups were held.  A questionnaire was administered and social groups identified as part of the adaptive capacity needs assessment.  The major social groups included Community Based Organizations (CBOs), Churches, NGOs, etc.  As part of the adaptive capacity needs assessment, a stakeholders’ workshop was conducted at the Mwingi District Headquarters on 14th and 15th November 2005.

Drought impacts on Livelihoods

55.  The impacts of droughts on crop production include reduced crop yields, total crop failures, influence on the choice of the types of crops grown, as well as crop diseases.  The major crops grown include maize, beans, green grams, cow peas, sorghum, and millet.  There has been a general shift from indigenous crops, which are highly drought tolerant, towards maize, and bean production, which are considered more modern and fashionable.  Most droughts do result in near total crop failure.

56.  Droughts have had numerous socio-economic impacts, which include reduced farm labor because some households engage in alternative means of livelihood such as working as farm laborers elsewhere and as casual employees in urban centers.  Additional labor is also required because animals have to be moved to distant locations for grazing.  A summary of these impacts is given in Table 2.2 below.

Table 2.2.  A summary of impacts of droughts in Mwingi District

| Impacts of droughts |  |  |  |
| --- | --- | --- | --- |
| On crop production | On the environment | On biodiversity | Socio-economically |
| Reduced crop yields Total crop failures Reduced variety of crops grown Land degradation Contributing to crop diseases | Reduction of water supply Reduction of livestock forage supply Biodiversity reduction (see adjacent column) loss of some highly palatable forage species | Extinction of some vegetation and animal species e.g. (given in Kikamba language) Mbeea – grass type Ngwai – bird type Ngunda Aithi Kithanze Kilili Kimuu Mbeetwa Kilia | Food relief Rural-urban migration Poor household nutritional levels Sale of family livestock poor livestock health high livestock disease incidences high school drop-out rates Increased poverty levels Conflict in resource use Famines and starvation Increased food insecurity levels |

57.  The major environmental hazard in Mwingi district is drought (see Figure 2.1).  Water supply has been identified as the major need in the district, particularly during the drought periods.  There are no sufficient water sources, and water levels in the shallow wells dug near streams either gets significantly low or dry up during the dry periods.  The population also has to walk long distances in search for water for both domestic use and livestock watering.  Droughts usually increase food insecurity through frequent crop failures and decreased forage supply for livestock.  Also identified is increased occurrence of diseases during periods of droughts, which is worsened by inadequate medical facilities in the study area.

58.  The most recent report from the Kenya Food Security Steering Group (KFSSG, January 2006) shows four consecutive seasonal rainfall failures that have resulted in depletion of food at household level, and about 90% of the population relying on food purchased from other Districts.  Major contributing factors to food insecurity in Mwingi District include lack of water for both human agriculture and livestock production, as well as lack of employment opportunities.  Households reported increased sales of livestock, especially cattle and goats, so as to purchase food.  This has depleted household resources and thereby increasing their vulnerability.  The yields of various crops for Mwingi district for the two cropping seasons in a year are show in Table 2.3 below.

Figure 2.1 Major Environmental hazards in Mwingi District.

Table 2.3:  Production achieved for main food crops in the last five seasons

| Type of crop | Yield(number of 90kg bags) -Long rains |  |  | Yield(number of 90kg bags) Short rains |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2003 | 2004 | 2005 | 2003/2004 | 2004/2005 | 2005/2006 |
| Maize | 9005 | 0 | 1129 | 184788 | 91945 | 0 |
| Sorghum | 9520 | 0 | 5364 | 80934 | 46935 | Negligible |
| Millet | 171160 | 0 | 8388 | 105280 | 68560 | Negligible |
| Beans | 4208 | 0 | 541 | 77523 | 40665 | 0 |
| Cow/peas | 14583 | 0 | 3504 | 131623 | 65660 | Negligible |
| Pigeon/peas | 2228 | 1557 | 13716 | 62288 | - | - |

Source: Mwingi District Short rains assessment Report (January, 2006)

Drought Coping strategies

59.  The communities within the UNDP pilot sites have developed various drought coping strategies and adaptation mechanisms in order to counter their impacts.  Table 2.4 gives a summary of these strategies and adaptation mechanisms.

Table 2.4.  Summary of mechanisms for coping with drought

- Mixed cropping

- Digging of shallow wells

- Diversification of livelihoods e.g.  bee keeping, venturing into small scale business

- Animal stock reduction to conserve forage

- Reliance on natural resources, e.g.  charcoal burning

- Drought tolerant crops such as sorghum, cowpeas, millet, cassava

- Extensive soil and water conservation measures

- Stockpiling of food reserves from good harvest years

- Sale of livestock during period of scarcity

- Paddocking as part of forage conservation

- Use of organic manure to enhance productivity

- Famine relief (mwolio)

- Urban migration

- Revolving group loans

60.  Drought coping strategies aim at increasing diversification of crops or mixed cropping, digging of shallow wells, and diversification of livelihoods e.g.  Bee keeping, venturing into business.  Other adaptation mechanisms include livestock “loaning”, emergence of several self-help groups, diversification of livestock production or keeping of few and different animal types in order to conserve forage, hiring of pasture, charcoal burning, protection of water sources by use of by-laws, and growing of drought resistant crops such as sorghum, cowpeas, millet, cassava.  Other coping strategies include extensive soil and water conservation measures, use of manure to increase yields, stockpiling of food reserves from good harvest years, sale of livestock during period of scarcity, “paddocking” as part of forage conservation, use of crop of residues to feed animals during droughts, use of manure to enhance productivity, sale of pasture for cash, hiring or leasing of grazing pastures, move animals to other areas (though not very common), and use of certain parts of plants such as acacia pods.

Challenges

61.  The following are among the challenges that the UNDP component of the joint project will address during the implementation phase: lack of water which is the major limiting factor in the copping mechanisms of the people of Mwingi; encouraging farmers to resort back to the indigenous crops which they consider unfashionable, yet are highly drought tolerant and will help to improve food security situation; creating awareness and incorporating suitable agro-forestry practices in the farming system as part of environmental and soil conservation measures; educating farmers on water harvesting techniques as means of enhancing water supply for domestic use and crop production.  Other challenges include identification of alternative sustainable livelihoods and adoption of the same by communities and reduction of destructive deforestation for charcoal burning and wood carving.  Among the major challenges that this project will address is piloting and testing coping strategies and capacity development to confront and overcome climate risks and enhancing resilience through diversification of livelihood options.

Barriers to adaptive capacity to climate change

(a) Household level Barriers

62.  Individual households rely mainly on single livelihood strategies and they are therefore vulnerable to the effects of climate change.  Within a certain community, very little in terms of diversification of livelihoods are observed, making communities also vulnerable.  Within a community, more than 90% of the households would be involved in only one or two livelihoods; either small scale farming or small scale agro-pastoralism.  Barriers to more diversification arise from lack of investment financing and to markets, which limit opportunities for income generation.

Enhanced Household capacity to cope with drought and climate change hanced

# Sustainable livelihoods

Enhanced use of climate information

# Climate risk integrated across sectors, community services and programmes

Diversity in food & income sources

Access to markets improved

Develop climate risk management technical skills of district agents

Integrated drought information system

Improved sector policies and institutional design

Improve household life skills

District

Drought plan

Skilled community level practitioners

Informed policy makers

Climate risk management training

Framework for community participation in decision making

Improve agro -meteorological monitoring & forecasting & info.  Dissemination for the region

Micro-level

Macro-level

Information and advocacy

Trained government, NGO & private sector policy & decision makers

Enhanced community participation in decision making on climate risk

Support small to medium scale adaptation projects

Improved agriculture Skills

Improve Access to drought proofing Technology & support services

Decision support tools and training for extension agents & natural resource managers & NGOs

Policy advocacy

Env.  Quality improved

Mobilize resources

Improve CBNRM

Selected as possible priority intervention by communities and stakeholders

63.  As the ecosystems in ASAL areas are fragile, dependence on natural resource based livelihoods are already unsustainable, especially with increasing population pressures.  Climate change will make the situation much worse, thereby increasing the level of community vulnerability.

(b) Institutional

64.  Institutions at national and local level have responsibilities in terms of economic planning and development.  In some cases, the effectiveness of these responsibilities are constrained by capacity, unclear scope and alignment with other relevant initiatives and including limitations in enforcement methodologies for institutions to fulfill their mandates.

(c) Systemic

65.  Barriers to incorporate policy on climate change issues emanate from widespread acceptance that drought and climate variability and change are acts of God and are inevitable.  As such, there is some hesitation to integrate climate change risks into national economic planning and development.  There is also the misconception that climate change is a future phenomenon which is very uncertain and therefore there is little economic justification to pay too much attention to it at present.  At the community level, such barriers are compounded by the repeated failure of existing systems, such as forecasting systems, as useful tools for climate change risk management.  In particular, there is reduced confidence in the usefulness of such tools, if properly used to assist decision-making capacities.

# PART II:  Strategy

# Project Rationale and Policy Conformity

66.  The joint UNDP-WB KACCAL project – including this UNDP-managed component– is submitted to the Special Climate Change Fund (SCCF). The project builds on the Arid Lands Resource Management Project (ALRMP II) project, a long standing Government program for rural development in the ASALs that has been successful in reaching marginalized communities and in establishing sound implementation systems for drought risk management. ALRMP originally started as an emergency drought recovery operation in 1994 (Emergency Drought Recovery Project, Cr. 2460). It was realized that a longer term program aimed at building a drought management system as well as community capacity to cope with drought was needed. Two phases of this program have been supported so far - ALRMP I (Credit 2797) with US$ 21m in 1996 and ALRMP II (Credit 3795) with US$ 60m in 2003. A supplemental credit for US$ 60m in 2006 expanded the scale and scope of operations, and replenished its depleted drought contingency fund. The project was also extended to June 2010. ALRMP now covers a total of 28 arid and semiarid districts and has strengthened its focus on natural resource management, now a distinct component. ALRMP’s strengths include a sound decentralized institutional structure, and effective coordination mechanisms at the national, district and community level which have resulted in an effective multi-sectoral approach to development. Short response times to drought stress, reduced distances to key social services, as well as diversification of livelihoods have been some of the key results of the program. ALRMP supported the establishment of the Kenya Food Security Meeting (KFSM), an effective mechanism for inter-government and donor-Government coordination on drought and food security at the national level. The KFSM is co-chaired by the ALRMP on behalf of Government and the World Food Program (WFP) and consists of key sectoral ministries and external partners. The KFSM continues to play a key role in overall drought management and is formally linked with Government’s drought and disaster coordination mechanisms.

67. The ALRMP catchment area is clearly affected by the rising risks of climate variability and change, and the program provides a very effective delivery mechanism for increasing the adaptive capacity of the most vulnerable segments of the population. KACCAL is consistent with the guidelines of the Special Climate Change Fund (SCCF) addressing several of its priority areas, including: water resource management, land management, agriculture, and fragile ecosystems. Through KACCAL, SCCF/GEF incremental support would enhance the climate information base; strengthen the adaptive capacity of relevant stakeholders and mainstream climate risk management into its development plans and investment programs.

Project Rationale

68.  The overall strategy of the UNDP-managed component of the KACCAL project is to enhance adaptive capacity to drought (and flood) in the pilot area.  Consultations with key stakeholders during the preparatory phase indicated that the priority needs to enhance adaptive capacity by piloting risk management strategies including enhanced access to and management of water for irrigation, promotion of indigenous crops that more resilient to anticipated climate (and improved access to markets for these crops), promoting livestock varieties that are more suited to the climate, development and promotion of alternative livelihood opportunities (such as beekeeping activities), strengthening climate risks management skills of extension workers whose role is to support household and community based projects, improving the flow and use of early warning and seasonal forecast information in community practices.  Training materials for climate risk management will be prepared and disseminated to other areas of the district as well as other parts of the country.

69.  The strategy adopted in this the UNDP-managed component of the KACCAL project builds on the development baseline, and includes additional activities to increase adaptive capacity to cope with drought under changing climatic conditions.

# Project Goal, Objective, Outcomes and Outputs/activities

70.  The goal of the overall UNDP-WB project is to enhance the resilience of communities and the sustainability of rural livelihoods threatened by climate change, in the arid and semi-arid lands of Kenya As a contribution to the achievement of this goal, the joint project objective is to increase the capacity of communities in the selected districts of the ASALs to adapt to climate variability and change.  In order to achieve the overall project objective, the following three project level outcomes will be supported by the UNDP-managed component of the KACCAL project.

Component 1: Climate information products, policy and advocacy

Outcome 1:  Enhanced capacity of national and regional stakeholders to plan, manage and implement climate change adaptation measures (SCCF Increment US$ 0.33 million).

Output 1.1: Targeted knowledge-based tools developed for effective climate risk management.

Activity 1.1.1 Efficient integrated drought information system

71.  This output focuses on the establishment of an integrated drought/flood early warning system or alternatively, the harmonisation of the existing early warning initiatives currently in place to include climate change risks.  A variety of measures will be tested in pilot sites (including Mwingi district) that increase the capacity of communities to reduce the likely impacts of anticipated drought/flood.  In addition, UNDP will support the establishment of a district-based integrated socio-economic, climatic information and environmental database system to support vulnerability/risk mapping and the results of climate change impact assessments for use by all stakeholders.  Information on forecasted stream-flow data, mid- to long-term weather forecasts, optimal crop, and livestock growing conditions, among other data that supports effective climate risk management.  In order to achieve this, UNDP will ensure collaboration with key stakeholders including the National Environment Management Authority, Kenya Meteorological Department, the United States Geological Survey (to obtain stream-flow data), FEWSNET, ICPAC, Ministry of Water Development, World Food Development Programme, FAO etc.

72.  This following indicative activities are envisaged:

- Collaboration with other development agencies to generate drought and early warning information requirements for planning and decision-making

- Collaborate with other agencies to establish a system that will provide near real-time early warning information through the harmonization of the various early warning information generators

- Collect and establish a historical and current production database for purposes of validation of the early warning information

- Support the documentation of existing indigenous knowledge system already being done by ICPAC and have it incorporated in the modern early warning system.

- Design and implement a socially-relevant drought information system

- Incorporate or help enhance the participation of the private sector in support and provision of early warning information

Activity 1.1.2  A platform for exchange of knowledge.

73.  The establishment and operation of a knowledge platform will improve the effectiveness and efficiency of the KACCAL project vis-à-vis the Coping with Drought and Climate Change projects in Ethiopia, Mozambique and Zimbabwe by exposing national teams to wider experiences than would otherwise have been possible.  It also means that project results will be more widely applicable.  The operation of the platform will involve several types of learning events, and indicative activities under this Output include:

- Documentation and reporting of good practices and success-stories.  The local implementing agency will be responsible for developing a system of reporting aimed at domestic dissemination.  In addition, however, the local implementing agency and UNDP Country Office will be responsible for regular reporting to the regional hub (The Drylands Development Centre), which will capture and disseminate lessons (see TORs in Annex 2).

- Learning tours.  The project will support replication and learning opportunities.  Farmers, and policy makers will have opportunities to visit pilot sites and other drought-affected sites in Kenya, to learn first-hand both of the impacts of drought and of measures that can increase adaptive capacity to deal with climate change.  Lesson from other pilot sites in other countries will be disseminated in appropriate ways so that there is maximum opportunity to learn from experiences in differnt climatic and socio-economic conditions.

Output 1.2:  National and regional coordination and information sharing improved, for effective climate risk management.

Activity 1.2.1 Interaction between stakeholders in the district enhanced.

74.  At the district level, the UNDP-managed component of the KACCAL project will facilitate and foster the formation of networks as well as creating a forum for monthly interactions and information sharing and exchange among the stakeholders in the project area.  In order to achieve this, the following activities will be carried out:

- Creating partnerships and networks among government departments, NGOs and CBOs working in Mwingi and other districts.

- Create awareness and interactions among the various stakeholders involved in environmental conservation and arid lands management in the project area.

- Formulate and support outreach programmes with sectoral government departments and other stakeholders

Activity 1.2.2 District drought preparedness plan implemented.

75.  Collaboration with the National Disaster Coordination Center and ALRMP will take place to assist the District Development Committee and other stakeholders to prepare and implement a district drought/flood preparedness plan.  Activities which may be undertaken to achieve this include:

- In collaboration with local stakeholders and development agencies, use drought information to identify priorities for district-level drought preparedness

- Formulate Drought/Flood Preparedness Plan

- Establish the technical capacity to implement plan.

- Support the National Disaster Coordination Center and ALRMP in implementing priority actions to increase drought preparedness at the district level.

Output 1.3:  Advocacy and outreach programme prepared and conducted for replication of adaptation measures.

76. UNDP, in collaboration with other partners, will develop and implement an advocacy programme to have climate risk management incorporated into agricultural sector policies and national development plans.  Use of policy briefs, posters, workshops and media campaigns will be adopted to facilitate this project.

- SCCF funds will support the preparation and distribution of policy information and materials.  The information in the materials should be simple and illustrative in form.

- The project team will prepare and host empowerment workshops for government officials, officials from NGOs and CBOs and also for local farmers and pastoralists in order to enable experience sharing

- The project will collaborate and support NGOs, CBOs and other development partners in carrying out the empowerment of local farmers and pastoralists

Output 1.4:  Adaptation learning disseminated through national, regional and international networks.

77. Adaptation learning will be an important outcome of the project. Lessons from these initiatives will be a valuable contribution to UNDP’s Adaptation Learning Mechanism, an initiative that is designed to contribute to the integration of adaptation to climate change within development planning of non-Annex I countries, and within the GEF’s portfolio as a whole. Some of the most salient learning points will be on the question of adaptation financing needs, and on efficient ways of allocating public financing to adaptation. The most pressing of these questions include:  identifying feasible and replicable adaptation options, assessing the costs and benefits of adaptation, finding ways to ensure financial sustainability, sequencing of adaptation measures, exploring the catalytic role of public policy and financing.  The project will contribute learning to the Adaptation Learning Mechanism.

Component 2: Supporting climate risk management at district and local levels

Outcome 2: Enhanced capacity of district and local level stakeholders to plan, manage and implement climate change adaptation measures (SCCF Increment US$ 0.2 million).

Output 2.1: Community-level capacity increased to undertake adaptation measures.

Activity 2.1.1 Increased awareness among relevant governmental departments, NGOs, and the private sector on integrating climate risks.

78.  This will be achieved through the following indicative activities:

- Creating partnerships and networks among the various stakeholders in order to enhance collaboration.

- Designing and implementing awareness programmes tailored to the needs and capacities of different stakeholders.

- Conduct training workshops on integrating climate change risks into policy formulation.

Activity 2.1.2 Natural resource managers, extension staff, and local community members trained in proper use of climate information.

79.  This activity, to be undertaken in collaboration with other partners, will target key natural resource managers, extension workers and others, will provide training on utilizing data on climate, socio-economic and ecosystem conditions for climate-sensitive decision making.  This information will be used to assist communities to plan to respond to drought.  It will lead to integrating climate information on the development processes and decision making mechanisms in the district.  This output will be achieved through implementation of the following indicative activities:

- Prepare training materials on climate change risk management

- Organize and deliver training courses targeting different stakeholder groups.

- Develop the institutional capacity to integrate drought information in development planning at local and district levels.

Activity 2.1.3 Extension personnel trained in drought related participatory rural appraisal (PRA) and networking techniques

80.  The project team, in collaboration with other partners will strengthen capacities in government,  NGO and CBOs institutions in the district to provide ongoing drought and climate change related participatory rural network training for extension staff, who will in turn train communities in the use of participatory assessment methods for drought mitigation.  The project will write and disseminate  training mannuals for trainers.  Activities to implement this output will be:

- Conduct a capacity needs assessment for enhancing application of climate and other information in decision support at community level.

- Facilitate extension staff and identified personnel from NGOs to undertake some short-term training course in drought early warning systems.

- Enhance an institutional integration and network system

Component 3: Community driven initiatives for climate resilience

Outcome 3: Enhanced communities’ ability to plan, manage and implement climate-related activities

(SCCF Increment US$ 0.40 million).

Output 3.1: Community based micro-projects supported

Activity 3.2.1 Community-identified interventions to increase capacity to cope with drought

81.  The project team will provide financial and technical support to communities within the pilot sites to design and undertake a number of small-scale to medium size projects that help in increasing their capacity to cope with drought.  The projects will involve the implementation of locally-developed coping mechanisms such as livestock development, reduction in erosion of top soils, water harvesting techniques and promotion of indigenous cropping systems with the added extension that climate change risks are integrated into the design of these community-based activities.  Activities include:

- In collaboration with local development agencies, and on the basis of capacity assessments undertaken during the preparatory phase, identify priority interventions to increase capacity to cope with drought, through a participatory process involving the targeted communities

- Undertake community workshops to scope priority actions and establish which will have positive impacts.

- Develop an overall plan for implementation of priority interventions,

- Mobilize technical support to implement priority interventions

- Support communities in implementing priority interventions

- Document experiences and lessons learnt

# Project Indicators, Risks and Assumptions

82.  Indicators for the UNDP-managed component of the KACCAL project were developed on the basis of the following criteria:

- Impact in terms of improving household food security and quality of local environment

- Sustainability of benefits in the long-term in social, environmental, technical, economic and financial terms.

- Institutional capacity development of all stakeholders, and

- Replicability from pilot site to other geographical areas and upward to national policy level.

83.  Indicators at the level of Objectives

- By the end of the project, the level of community awareness of climate change risks within the pilot sites to have been raised by75%.

- By the end of the project, the level of climate risk management skills at the project sites will have increased by more than 50%.

84 Indicators at the level of Outcomes

Outcome 1:

- At the end of the project, mechanism for applying climate risk management information will be established and policy needs awareness created within the project sites.

- By the end of the project, community leaders in the project pilot sites are able to describe at least one lesson in coping with drought learnt from another site (not necessarily in Kenya)

- By the end of the project, senior officials in relevant sectoral ministries are able to describe strategies to increase adaptive capacity to cope with drought from both Kenya and neighboring countries.

Outcome 2:

- By the end of the project, more than 90% of extension staff and, NGOs and private organizations working with the communities have skills in effective climate risk management practices

- By the end of the project, more than 50% of the community, extension workers and development partners to be using climate information for decision making

Outcome 3:

- By the end of the project, at least 75% of the households are food secure within the UNDP-managed pilot sites

- By the end of the project, the yields among small-scale farmers will be increased by 10%, and livestock productivity increased by 10%.

- By the end of the project, at least 50% of the farmers and pastoralist  at the UNDP-managed project sites will be aware of the relevant policies and institutions dealing with climate risk management

- Throughout the project, annual PIRs do not identify access to technical inputs as a constraint to implementation.

85. The project will contribute to adaptation learning in the wider KACCAL project described in the WB project document.  Key indicators in the WB-supported project are as follows:

- Climate risk management mainstreamed into district management and community action plans in pilot areas;

- Percent of community adaptation projects rated satisfactory or better by participating communities;

- Percent of ALRMP projects screened for improving (adapted) response to climate risk;

- Number of communities which consider the provided climate information services as relevant (i.e. whose decisions are affected by the capacity they receive).

### Assumptions

86.  The generation of Outcomes through the proposed Outputs for the UNDP-managed component of the KACCAL project is based on a number of assumptions, which are described in the logframe matrix in Section II.   One key assumption is that drought is the only natural extreme event occurring in the target District during the project lifetime.

87.  Most other assumptions relate to commitment of the stakeholder.  This includes commitment from the Government of Kenya, the FFS and local government staff, extension workers and local beneficiaries.  The participatory approach used in formulation of the project strategy revealed that such commitment does currently exist.  The commitment of government agencies also assumes that broader political interference does not affect project implementation.

88.  The dissemination process will be aided through community radio, and there is consequently an assumption made that KMD will commit to establishment of RANET community radio.  Again, the participatory approach, which involved discussions with KMD, revealed that this assumption is currently valid.

### Risks

| Risk | Risk Rating | Mitigation Measures |
| --- | --- | --- |
| Sustaining coordination with KSFM and other disaster management platforms due to change in institutional home | M | Under the Coalition Government, with reorganized/divided ministries, ALRMP was moved to the newly established State Ministry for Development of Northern Kenya and Other Arid Lands reporting to the Prime Minister’s Office. This could potentially affect the leverage and coordination power of ALRMP which it had in its previous location (Office of the Prime Minister). However, the ALRMP and the Bank have discussed this with the highest level of the GOK and been assured that the change will not negatively affect the implementation of ALRMP and KACCAL. The program continues to straddle the two ministries to support various activities and functions managed by both entities |
| Alternative sustainable livelihood strategies to pastoralism are not taken up in the arid lands | H | Diversification in the arid lands has been limited, hampered by lack of market access, credit availability and linkages to the rest of the economy. This project cannot alone change these fundamental constraints. However, the project will provide support for creating a more conducive environment for diversified sustainable livelihoods, particularly in increasing the sustainable extraction/production and value addition of dryland products. The project will provide technical assistance and facilitate public-private-community partnerships towards this objective. |
| Continued and growing conflict, specially in the arid districts | M | Conflict management has been an integral part of ALRMP implementation, in recognition of the severe competition for resources in the Arid Lands and spillover from conflict in neighboring countries. The potential for conflict still exists and could increase as the pressure over resources intensifies. By helping reduce the vulnerability of communities in face of resource scarcity, the project is contributing to reducing the sources of conflict. |
| Technical capacity and services available are inadequate to support local development | M | Capacity constraints in the arid lands are prevalent in many sectors. The project alone will not be able to address general capacity constraints but the project includes a substantial focus on capacity strengthening – both in technical issues of climate risk management for service providers, policy makers as well as in community capacity to integrate climate risk in their development plans and in monitoring. The project will use the same mechanism as the ALRMP, i.e. mobile extension teams for this purpose. |
| Recurrent droughts during the implementation period of the project keep diverting attention away from long-term planning | M | This risk is being mitigated partly by the fact that the baseline project has already created substantial capacity to effectively respond to these short-term emergencies, and partly by building capacity among the key agencies to be improve the response to immediate catastrophes. In addition, it should be noted that recurrent extremes can also provide an additional motivation to address the underlying long-term vulnerabilities that might have remained hidden or tolerable under normal climate conditions. |

### Additionality

89.  The joint UNDP-WB project seeks to enhance local capacities to address anticipated future impacts of long-term climate change.  This requires developing the adaptive capacity of local and national stakeholders to cope with increased frequency and intensity of drought, which the INC has identified as a major consequence of climate change.  This means that project stakeholders need to build their capacity to adapt to changing climatic conditions.  Thus, for example in a scenario without climate change, diversification of agricultural systems as a means of promoting sustainable land management would constitute a sufficient intervention.  However, the project strategy presented here also builds capacity to continually review the sustainability of such systems and adapt them as the impacts of climate change alter the underlying drivers of productivity.  As such, the project meets the eligibility criteria of the SCCF.

90.  Adaptation to climate change starts with an understanding of current coping strategies for dealing with droughts experienced under current climate variability.  Under conditions of climate change, droughts in Kenya will become both more frequent and more intense.  SCCF funding to this project will support the additional cost of the adaptation activities.

91.  The baseline scenario for this project represents a “business-as-usual” wherein Kenya undertakes only those activities in its current baseline development planning.  Rural communities will continue to rely on current coping strategies, without due consideration of the impending worsening risks.  These strategies will therefore become inadequate as droughts (or floods) increases in frequency and intensity.  SCCF funds will contribute towards enhancing resilience to impending climate change related risks, particularly at the community level.  SCCF funding will cover the difference between relative costs associated with the baseline scenario and the alternative scenario of enduring climate change resilience.

### Expected National and local benefits

92.  The outputs from this UNDP component will assist communities at the local level to address climate change risks affecting food security and livelihoods.  At the national level, the joint UNDP-World Bank project will contribute towards the formulation of suitable policies to support sustainable utilization of ASALs in the context of climate change.  The other benefits include:

- Enhancing the resilience of agricultural land to climate risks;

- Empowering communities to overcome climate induced pressures through the development of sustainable forms of diversified agriculture (both crops and livestock);

- Enhancing food security amongst the communities and farm family income through the sustainable promotion of indigenous food crop production;

- Improved water tables that will sustain the shallow wells;

- Enhanced recharge groundwater due to the re-establishment of land cover through afforestation activities

Costs to be borne by the SCCF

93.  The SCCF contribution to the project will be allocated for activities presented above following the principle of additional cost reasoning.  That is, SCCF resources will complement ongoing activities that are to be funded as part of ongoing baseline development (“business-as-usual” scenario).  SCCF resources will ensure that the alternative scenario, where specific development activities are resilient to long term climate change, is achieved.

94.  The total cost of the alternative is estimated to be $2,000,000.  Of this total, the costs of the baseline scenario are estimated to be $1,000,000, and the additional costs of the alternative are $1,000,000.  Of this total, $1,000,000 will be contributed as co-financing from the government of Kenya.  The contribution requested from the SCCF amounts to $1,000,000, which represents the costs associated with activities necessary to build capacity to adapt to long term climatic changes.

# Country Ownership: Country Eligibility and Country Drivenness

95.  Kenya ratified the UNFCCC on 30th August 1994 and is eligible for financial support under Annex 1 of the UNFCCC, and is also eligible for technical assistance from UNDP.

96.  Kenya expressed interest in this work by participating in a farmer-focused survey on accessibility and use of contemporary and indigenous climate information conducted in 1999.  Since then, through regular consultations between UNDP-DDC, UNDP, World Bank and the Government of Kenya, possible interventions on drought mitigation and climate adaptation have been identified.  Kenya’s Poverty Reduction Plan (PRSP) emphasizes the importance of drought management and food security.

97.  The National Communication for Kenya formed an important starting point in project design and site selection.  The information in the National Communication was used in identifying areas vulnerable to climate change, in terms of projected scenarios of rainfall and temperature changes.  The APF provided guidelines on how to engage stakeholders, which was an important element of project design.

98.  Existing adaptation and vulnerability impact assessments for Kenya cover impacts on six vulnerable sectors, which include agricultural products (such as maize, beans and livestock) and water resources (targeting storage, recharge, and quality).  Other sectors include aquatic and coastal resources (influencing lake levels, fisheries, marine, and sea level rise), human health (such as malaria, cholera, trypanosomiasis, respiratory diseases etc.), terrestrial ecosystems (pastoral systems, changes in forest cover, etc.), human settlements, and socio-economic settings (such as population displacements, rural-urban migration, water pollution, etc).  In order to reduce climate change impacts in important economic sectors such as agriculture and water resources, it is therefore necessary to identify relevant measures for adaptation.

# Sustainability

99.  Local stakeholders contributed to the development of each of the project components during the planning phase.  Opportunities to take ownership of project activities, and direct the scope of the activities were facilitated through national stakeholder workshops (to identify priority needs); community-engagement through site visits and needs assessment surveys and individual consultations.

100.  The project seeks to remove barriers to adaptive capacity that currently limit the ability of communities to cope with climate impacts, and sometimes leads to maladaptive coping strategies.  For this reason, recurrent costs and dependency in the UNDP-managed pilot sites are likely to be negligible, if any.  The proposed interventions will enhance capacities of communities in to implement strategies that reduce climate risks and therefore reduce the need for additional support.  The assumption is that community support for the project, which currently exists, is not eroded due to reasons beyond the control of UNDP and its partners.

101.  By integrating climate risk management into existing planning plans, policies and programmes (which in large part is achieved by including the Ministry of Agriculture and the Office of the Prime Minister (ALRMP) involved in the planning and implementation of this project), the financial cost of implementing measures will also be mainstreamed in the long-term.  In such terms the project builds on existing programmes and plans that include the definition of financing strategies and mechanisms.  It will also reinforce and enhance on going activities from diverse organizations – educational, environmental, etc., thus, increasing possibilities of long term financial sustainability.  In addition, as the proposal targets key elements of rural development, it is expected that national and local institutions will not only provide support for the initial and implementation phases, but also for further actions on climate risk management in rural areas.

102.  As climate change risk management needs to address socio–economic and political structures influencing/affecting rural development, efforts to achieve policy and programme transformations at sectoral, national, and local scale need to be well supported by an institutional network.  The linkage of this project to a wider World Bank-UNDP initiative therefore ensures that institutional sustainability is promoted.  Several governmental institutions have demonstrated their commitment to this adaptation initiative both as active counterparts and as co-financers of activities regarding the enhancement of ongoing actions on land management.  Amongst those institutions involved in the process are the Ministry of Agriculture and the Office of Prime Minister.

103.  A favorable political environment has led this process, from national government stakeholders to authorities at the local level at the district level, especially the ones from Mwingi, to national networks of environmental NGOs.  As baseline organizations have taken part of the preparatory process and others are getting involved as well for the implementation phase, the project has the conditions to be supported not only by an institutional network but also by a social one, which is a key requirement if outcomes are intended to last during and beyond the project time line itself.  Various awareness raising initiatives, in both the UNDP and World Bank managed components of this joint project will ensure there is social sustainability.

# Replicability

104.  The approach of the joint UNDP-WB project (and the UNDP-managed component of the KACCAL project in particular), if successful, is replicable across different ASAL areas of Kenya that face climate induced drought problems.  Two intertwined processes and structures are required: one for horizontal programming and another for collaborative government-community partnerships.  This framework relies upon two parallel streams: one at the community level and the other at the government wide level.  The community level process starts with the development of regional/local adaptation strategies, identifying sustainable adaptive capacity indicators; developing community operational plans; identifying and allocating adaptation plan resources; implementing these plans; and monitoring and evaluating the strategies.  The need for a government level process stems from the recognition that such a process is needed to effect horizontal programming and integrated decision making.  The project will build on existing structures and processes, rather than by passing or creating new ones.

105.  For the project to transition to a national programme and be of benefit to communities beyond the pilot sites, there needs to be demand for integrating climate change risks into drought (flood) management programmes.  The role of the pilot sites, in this context, is to demonstrate the benefits and effectiveness of a range of climate risk management strategies and measures, awareness building, training of relevant policy makers and community development practioners as well as community members.  SCCF resources will also facilitate the involvement of stakeholders from other geographical areas in capacity development initiatives, as well as the production and dissemination of lessons learned.

### Cost Effectiveness

106.  The selected project design was considered to be the most cost effective approach to adaptation in Kenya.  The project will focus on the lower cost option of climate proofing land-use planning and management processes rather than on wide scale and high investments of hard-measures.  Building adaptive capacity through incorporating climate change considerations and disaster risk management into on-going land use planning process is expected to increase resilience of rural development initiatives to climate change.  Furthermore it will provide the information necessary to make decisions and trade-offs regarding alternative land-use options.  It will also inform future decisions regarding other forms of protection such as high investment structures in very specific cases where climate change cannot be addressed through increasing the resilience of communities and where these measures may be valid in view of highly significant negative impacts on economic and or environmental attributes.

107.  A number of alternatives were also considered to enhance cost effectiveness in terms of implementation costs.  Selection of sites for pilot demonstrations and of implementing partners considered the need to reduce the costs of setting up and monitoring on the ground actions.  Thus the project will maximize its cost effectiveness by building on existing initiatives and processes and by partnering with local institutions.  For example the Office of the Prime Minister (ALRMP) will provide its institutional capacities and experience to implement the activities related to integrated land and water management.  Together with the partnership with the Ministry of Agriculture, the project ensures and provides an economically effective way to work with municipal governments and institutions and actors on the ground.  By working with existing risk management institutions, the project outcomes regarding the reduction of vulnerability to climate change will be enhanced P.

108.  The project pilot demonstration activities will be implemented in a district that has already in place legislative frameworks and municipal capacities regarding land management.  In this context, relatively small additional efforts in implementing climate change adaptation measures are expected to produce considerable results improving current management practices and the overall rural development and management.

109.  Finally with regard to procurement of project inputs, standard procedures of the Government of Kenya and of UNDP will be carefully applied to ensure value for money in all purchases of goods and procurement of services for the project, and the project will use strict internal and external audit controls that meet international standards

# PART III: Management Arrangements

110.  This project document covers those activities under the KACCAL project which will be supervised by UNDP.  Co-management arrangements with the WB-supported KACCAL project will be agreed in the project start-up phase.

111.  In accordance with UNDP’s Results Based Management Framework, the project will be overseen by a Project Board, comprising UNDP, the World Bank, the Office of the Prime Minister (the Implementing Partner), the Ministry of Agriculture and Ministry of Livestock and Fisheries.  This Project Board, meeting on a quarterly basis, will advise the Implementing Partner during the execution phase and provide guidance on the complementary roles of UNDP and World Bank in this joint project.

112.  The ALRMP (Office of Prime Minister-OP) will be the Implementing Partner.  In consultation with the Ministry of Agriculture, the ALRMP/OP will oversee the implementation of the project.  This includes being responsible for financial accounting, project’s resources management and submission of financial and progress reports of the project to UNDP.  ALRMP/OP and MOA will provide technical support through co-financing and follow up on the project implementation in consultation with the PMU and UNDP CO.  ALRMP/OP will work through regional offices of the Ministry of Agriculture to facilitate project implementation.  It will ensure that the project is aligned with the work it is currently undertaking through agricultural extension services.

113.  ALRMP/OP will integrate this project into an existing project management unit (PMU).  Arrangements will be made to ensure that a project manager leads the project implementation.  National consultants will also be contracted (as required) to provide services related to the project implementation.  Procurement must follow established UNDP procedures.

114.  ALRMP/OP will submit regular progress reports to UNDP and undertake annual progress reviews, and oversee project monitoring and evaluation.  It will also be responsible to provide inputs necessary for successful project implementation (as in kind contributions) and host the project management unit.

115.  A district implementation committee drawn from technical staff from Government (Ministry of Agriculture, NEMA etc), Non Governmental Organizations, and private sector institutions will meet on a monthly basis to give technical advice to the UNDP component of the joint project.

116.  UNDP-CO will be responsible for the overall development and follow up program review, timely delivery, and leading and overseeing monitoring and evaluation.  It will also be accountable for the disbursement of project fund.  It will also establish and maintain financial accounts for the project as per established procedures.  The UNDP RTA (based in Pretoria) will provide strategic guidance to the project during implementation including technical input on project specific outcomes.

117.  In addition, collaboration with international organizations and private sector associations will be pursued to ensure a wide range of professional capabilities and functions in order to execute the project efficiently and effectively.  For example, it is anticipated that the Drylands Development Centre (DDC) will play a role in providing technical support for the regional component of this and the other Coping with Drought projects in Mozambique, Zimbabwe and Ethiopia (in the delivery of some elements of activities 1.1.2 as per details in Annex 2).  The roles of various partners will be clarified during the implementation phase by the Project Management Unit in consultation with the Implementing Partner, UNDP Regional Technical Advisor, and UNDP-CO.

118.  In addition, in order to accord proper acknowledgement to GEF for providing funding, a GEF logo should appear on all relevant GEF project publications, including among others, project hardware and vehicles purchased with GEF funds.  Any citation on publications regarding projects funded by GEF should also accord proper acknowledgment to GEF.  The UNDP logo should be more prominent -- and separated from the GEF logo if possible, as UN visibility is important for security purposes.

# PART IV: Monitoring and Evaluation Plan

Monitoring and Reporting

1.1.  	Project Inception Phase

119.  A Project Inception Workshop will be conducted with the full project team, relevant government counterparts, co-financing partners, the UNDP-CO, and representation from the UNDP Regional Coordinating Unit, as well as UNDP (HQs) as appropriate.

120.  A fundamental objective of this Inception Workshop will be to assist the project team to understand and take ownership of the joint project’s goals and objectives, as well as finalize preparation of the project's first annual work plan on the basis of the Logframe matrix.  This will include reviewing the Logframe (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise finalize the Annual Work Plan (AWP) with precise and measurable performance indicators, and in a manner consistent with the expected outcomes for the UNDP component.

121.  Additionally, the purpose and objective of the Inception Workshop (IW) will be to: (i) introduce staff with the UNDP expanded team which will support the project during its implementation, namely the CO and responsible Regional Coordinating Unit staff; (ii) detail the roles, support services and complementary responsibilities of UNDP-CO and RCU staff vis-à-vis the project team; (iii) provide a detailed overview of UNDP reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the Annual Project Implementation Reviews (PIRs) and related documentation, the Annual Project Report (APR), Tripartite Review Meetings, as well as mid-term and final evaluations.  Equally, the IW will provide an opportunity to inform the project team on UNDP project related budgetary planning, budget reviews, and mandatory budget rephasings.

122.  The IW will also provide an opportunity for all parties to understand their roles, functions, and responsibilities within the joint project's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for project staff and decision-making structures will be discussed again as needed, in order to clarify for all, each party’s responsibilities during the implementation phase for the project

1.2.	Monitoring responsibilities and events

123.  A detailed schedule of reviews meetings will be developed by the project management team, in consultation with project implementation partners and stakeholder representatives and incorporated in the Project Inception Report.  Such a schedule will include: (i) tentative time frames for Tripartite Reviews, Steering Committee Meetings, (or relevant advisory and/or coordination mechanisms) and (ii) project related Monitoring and Evaluation activities.

124.  Day to day monitoring of implementation progress will be the responsibility of the Project Coordinator, Director or CTA (depending on the established project structure) based on the project's Annual Work Plan and its indicators.  The Project Team will inform the UNDP-CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

125.  The Project Coordinator and the UNDP Technical Advisor will fine-tune the progress and performance/impact indicators of the project in consultation with the full project team at the Inception Workshop with support from UNDP-CO and assisted by the UNDP Regional Coordinating Unit.  Specific targets for the first year implementation progress indicators together with their means of verification will be developed at this Workshop.  These will be used to assess whether implementation is proceeding at the intended pace and in the right direction and will form part of the Annual Work Plan.  The local implementing agencies will also take part in the Inception Workshop in which a common vision of overall project goals will be established.  Targets and indicators for subsequent years would be defined annually as part of the internal evaluation and planning processes undertaken by the project team.

126.  Measurement of impact indicators related to global benefits will occur according to the schedules defined in the Inception Workshop and tentatively outlined in the indicative Impact Measurement Template at the end of this Annex.  The measurement, of these will be undertaken through subcontracts or retainers with relevant institutions (e.g.  Vegetation cover via analysis of satellite imagery, or populations of key species through inventories) or through specific studies that are to form part of the projects activities (e.g.  Measurement of carbon benefits from improved efficiency of ovens or through surveys for capacity building efforts) or periodic sampling such as with sedimentation.

127.  Periodic monitoring of implementation progress will be undertaken by the UNDP-CO through quarterly meetings with the project proponent, or more frequently as deemed necessary.  This will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

128.  UNDP Country Offices and UNDP RCUs as appropriate, will conduct yearly visits to projects that have field sites, or more often based on an agreed upon scheduled to be detailed in the project's Inception Report / Annual Work Plan to assess first hand project progress.  Any other member of the Steering Committee can also accompany, as decided by the SC.  A Field Visit Report will be prepared by the CO and circulated no less than one month after the visit to the project team, all SC members, and UNDP.

129.  Annual Monitoring will occur through the Tripartite Review (TPR).  This is

the highest policy-level meeting of the parties directly involved in the implementation of a project.  The project will be subject to Tripartite Review (TPR) at least once every year.  The first such meeting will be held within the first twelve months of the start of full implementation.  The project proponent will prepare an Annual Project Report (APR) and submit it to UNDP-CO and the UNDP regional office at least two weeks prior to the TPR for review and comments.

130.  The APR will be used as one of the basic documents for discussions in the TPR meeting.  The project proponent will present the APR to the TPR, highlighting policy issues and recommendations for the decision of the TPR participants.  The project proponent also informs the participants of any agreement reached by stakeholders during the APR preparation on how to resolve operational issues.  Separate reviews of each project component may also be conducted if necessary.

Terminal Tripartite Review (TTR)

131. The terminal tripartite review is held in the last month of project operations.  The project proponent is responsible for preparing the Terminal Report and submitting it to UNDP-CO and the Regional Coordinating Unit.  It shall be prepared in draft at least two months in advance of the TTR in order to allow review, and will serve as the basis for discussions in the TTR.

The terminal tripartite review considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its stated objectives and contributed to the broader environmental objective.  It decides whether any actions are still necessary, particularly in relation to sustainability of project results, and acts as a vehicle through which lessons learnt can be captured to feed into other projects under implementation of formulation.

131.  The TPR has the authority to suspend disbursement if project performance benchmarks are not met.  Benchmarks will be developed at the Inception Workshop, based on delivery rates, and qualitative assessments of achievements of outputs.

1.3.  	Project Monitoring Reporting

133.  The Project Coordinator in conjunction with the UNDP extended team will be responsible for the preparation and submission of the following reports that form part of the monitoring process.  Items (a) through (f) are mandatory and strictly related to monitoring, while (g) through (h) have a broader function and the frequency and nature is project specific to be defined throughout implementation.

(a)	Inception Report (IR)

134.  A Project Inception Report will be prepared immediately following the Inception Workshop.  It will include a detailed Firs Year/ Annual Work Plan divided in quarterly time-frames detailing the activities and progress indicators that will guide implementation during the first year of the project.  This Work Plan would include the dates of specific field visits, support missions from the UNDP-CO or the Regional Coordinating Unit (RCU) or consultants, as well as time-frames for meetings of the project's decision making structures.  The Report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 months time-frame.

135.  The Inception Report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners.  In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may effect project implementation.

136.  When finalized the report will be circulated to project counterparts who will be given a period of one calendar month in which to respond with comments or queries.  Prior to this circulation of the IR, the UNDP Country Office and UNDP’s Regional Coordinating Unit will review the document.

- Annual Project Report (APR)

137.  The APR is a UNDP requirement and part of UNDP’s Country Office central oversight, monitoring, and project management.  It is a self -assessment report by project management to the CO and provides input to the country office reporting process and the ROAR, as well as forming a key input to the Tripartite Project Review.  An APR will be prepared on an annual basis prior to the Tripartite Project Review, to reflect progress achieved in meeting the project's Annual Work Plan and assess performance of the project in contributing to intended outcomes through outputs and partnership work.

138.  The format of the APR is flexible but should include the following:

- An analysis of project performance over the reporting period, including outputs produced and, where possible, information on the status of the outcome

- The constraints experienced in the progress towards results and the reasons for these

- The three (at most) major constraints to achievement of results

- AWP, CAE and other expenditure reports (ERP generated)

- Lessons learned

- Clear recommendations for future orientation in addressing key problems in lack of progress

- Project Implementation Review (PIR)

139.  The PIR is an annual monitoring process mandated by the GEF.  It has become an essential management and monitoring tool for project managers and offers the main vehicle for extracting lessons from ongoing projects.  Once the project has been under implementation for a year, a Project Implementation Report must be completed by the CO together with the project.  The PIR can be prepared any time during the year (July-June) and ideally prior to the TPR.  The PIR should then be discussed in the TPR so that the result would be a PIR that has been agreed upon by the project, the executing agency, UNDP CO and the concerned RC.

140.  The individual PIRs are collected, reviewed, and analyzed by the RCs prior to sending them to the focal area clusters at the UNDP headquarters.  The focal area clusters supported by the UNDP M&E Unit analyze the PIRs by focal area, theme and region for common issues/results and lessons.  The TAs and PTAs play a key role in this consolidating analysis.

141.  The focal area PIRs are then discussed in the GEF Interagency Focal Area Task Forces in or around November each year and consolidated reports by focal area are collated by the GEF Independent M&E Unit based on the Task Force findings.

142.  The GEF M&E Unit provides the scope and content of the PIR.  In light of the similarities of both APR and PIR, UNDP has prepared a harmonized format for reference.

- Quarterly Progress Reports

143.  Short reports outlining main updates in project progress will be provided quarterly to the local UNDP Country Office and the UNDP regional office by the project team.  See format attached.

Periodic Thematic Reports

144.  As and when called for by UNDP, UNDP or the Implementing Partner, the project team will prepare Specific Thematic Reports, focusing on specific issues or areas of activity.  The request for a Thematic Report will be provided to the project team in written form by UNDP and will clearly state the issue or activities that need to be reported on.  These reports can be used as a form of lessons learnt exercise, specific oversight in key areas, or as troubleshooting exercises to evaluate and overcome obstacles and difficulties encountered.  UNDP is requested to minimize its requests for Thematic Reports, and when such are necessary will allow reasonable timeframes for their preparation by the project team.

- Project Terminal Report

145.  During the last three months of the project the project team will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the Project, lessons learnt, objectives met, or not achieved, structures and systems implemented, etc., and will be the definitive statement of the Project’s activities during its lifetime.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the Project’s activities.

- Technical Reports (project specific- optional)

146.  Technical Reports are detailed documents covering specific areas of analysis or scientific specializations within the overall project.  As part of the Inception Report, the project team will prepare a draft Reports List, detailing the technical reports that are expected to be prepared on key areas of activity during the course of the Project, and tentative due dates.  Where necessary this Reports List will be revised and updated, and included in subsequent APRs.  Technical Reports may also be prepared by external consultants and should be comprehensive, specialized analyses of clearly defined areas of research within the framework of the project and its sites.  These technical reports will represent, as appropriate, the project's substantive contribution to specific areas, and will be used in efforts to disseminate relevant information and best practices at local, national, and international levels.

- Project Publications (project specific- optional)

147.  Project Publications will form a key method of crystallizing and disseminating the results and achievements of the Project.  These publications may be scientific or informational texts on the activities and achievements of the Project, in the form of journal articles, multimedia publications, etc.  These publications can be based on Technical Reports, depending upon the relevance, scientific worth, etc., or may be summaries or compilations of a series of Technical Reports and other research.  The project team will determine if any of the Technical Reports merit formal publication, and will also (in consultation with UNDP, the government and other relevant stakeholder groups) plan and produce these Publications in a consistent and recognizable format.  Project resources will need to be defined and allocated for these activities as appropriate and in a manner commensurate with the project's budget.

2. Independent evaluation

148.  The project will be subjected to at least two independent external evaluations as follows:-

Mid-term Evaluation

149.  An independent Mid-Term Evaluation will be undertaken at the end of the second year of implementation.  The Mid-Term Evaluation will determine progress being made towards the achievement of outcomes and will identify course correction if needed.  It will focus on the effectiveness, efficiency, and timeliness of project implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about project design, implementation, and management.  Findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the project’s term.  The organization, terms of reference and timing of the mid-term evaluation will be decided after consultation between the parties to the project document.  The Terms of Reference for this Mid-term evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP.

Final Evaluation

150.  An independent Final Evaluation will take place three months prior to the terminal tripartite review meeting, and will focus on the same issues as the mid-term evaluation.  The final evaluation will also look at impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental goals.  The Final Evaluation should also provide recommendations for follow-up activities.  The Terms of Reference for this evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP.

151. Project mid-term and terminal evaluation will be carried out jointly with the WB-supported KACCAL project.

###### Audit Clause

152.

The project will be audited on a yearly basis for financial year January to December as per UNDP audit policies on NEX projects and GEF requirements, based on certified financial statements provided by MADRRM. The audits will be conducted by an independent commercial auditor engaged by UNDP.

Indicative Monitoring and Evaluation Work plan and corresponding Budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team Staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop | Project Coordinator UNDP CO UNDP |  | Within first two months of project start up |
| Inception Report | Project Team UNDP CO | None | Immediately following IW |
| Measurement of Means of Verification for Project Purpose Indicators | Project Coordinator will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members | To be finalized in Inception Phase and Workshop. Indicative cost $10, 000 | Start, mid and end of project |
| Measurement of Means of Verification for Project Progress and Performance (measured on an annual basis) | Oversight by Project Technical Advisor and Project Coordinator Measurements by regional field officers and local IAs | To be determined as part of the Annual Work Plan's preparation. Indicative cost $10, 000 | Annually prior to APR/PIR and to the definition of annual work plans |
| APR and PIR | Project Team UNDP-CO UNDP | None | Annually |
| TPR and TPR report | Government Counterparts UNDP CO Project team UNDP Regional Coordinating Unit | None | Every year, upon receipt of APR |
| Steering Committee Meetings | Project Coordinator UNDP CO | None | Following Project IW and subsequently at least once a year |
| Periodic status reports | Project team | 5,000 | To be determined by Project team and UNDP CO |
| Technical reports | Project team Hired consultants as needed | 10,000 | To be determined by Project Team and UNDP-CO |
| Mid-term External Evaluation | Project team UNDP- CO UNDP Regional Coordinating Unit External Consultants (i.e. evaluation team) | 10,000 | At the mid-point of project implementation. |
| Final External Evaluation | Project team, UNDP-CO UNDP Regional Coordinating Unit External Consultants (i.e. evaluation team) | 12,000 | At the end of project implementation |
| Terminal Report | Project team UNDP-CO External Consultant | None | At least one month before the end of the project |
| Lessons learned | Project team UNDP Regional Coordinating Unit (suggested formats for documenting best practices, etc) | 11,000 | Yearly |
| Audit | UNDP-CO Project team | 7,000 | Yearly |
| Visits to field sites (UNDP staff travel costs to be charged to IA fees) | UNDP Country Office UNDP Regional Coordinating Unit (as appropriate) Government representatives | 5,000 | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | US$ 80, 000 |  |

### 3. Learning and Knowledge Sharing

153.  The GEF’s Adaptation Learning Mechanism is designed to contribute to the integration of adaptation to climate change within development planning of non-Annex I countries, and within the GEF’s portfolio as a whole.  To support this goal, adaptation projects should generate knowledge that can help guide implementation of the GEF’s adaptation to climate change initiatives.  From the GEF family perspective, sharing knowledge among users will ensure that the GEF portfolio, as a whole, can benefit from the comparative strengths and experience of the various Agencies.  Results from the project will be disseminated within and beyond the project intervention zone through a number of existing information sharing networks and fora.  UNDP’s Regional Technical Advisor (based in Pretoria) should be consulted for guidance on the learning elements of this project.  A template for the learning element of this project, to be further refined by the Project Team, is attached in Annex 4.

154.  The project will participate, as relevant and appropriate, in UNDP approved networks.

155.  The project will identify and participate, as relevant and appropriate, in scientific, policy-based, and/or any other networks, which may be of benefit to project implementation though lessons learned.

# PART V: Legal Context

156.  This Project Document shall be the instrument referred to as such in Article I of the Standard Basic Assistance Agreement between the Government of Kenya and the United Nations Development Programme, signed by the parties on 17 January 199.  The host country implementing agency shall, for the purpose of the Standard Basic Assistance Agreement, refer to the government co-operating agency described in that Agreement.

157.  The UNDP Resident Representative in Kenya is authorized to effect in writing the following types of revision to this Project Document, provided that he/she has verified the agreement thereto by the UNDP Unit and is assured that the other signatories to the Project Document have no objection to the proposed changes:

- Revision of, or addition to, any of the annexes to the Project Document;

- Revisions which do not involve significant changes in the immediate objectives, outputs or activities of the project, but are caused by the rearrangement of the inputs already agreed to or by cost increases due to inflation;

- Mandatory annual revisions which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or take into account agency expenditure flexibility; and

- Inclusion of additional annexes and attachments only as set out here in this Project Document

# SECTION II: LOGFRAME

See next page

| Result | Indicator | Baseline value | Target and benchmarks | Means of verification and frequency | Assumptions |
| --- | --- | --- | --- | --- | --- |
| Overall Goal: To enhance the resilience of the communities, to climate change impacts in agricultural and pastoral systems in arid and semi-arid lands in Kenya |  |  |  |  |  |
| Project Objective: To increase the capacity of communities in the selected districts of the ASALs to adapt to climate variability and change. | 1. By the end of the project, the level of climate risk management skills and natural resource conservation activities at the project sites will have increased by more than 50%. | 1. Level of effective climate risk management skills and natural resource conservation activities within the communities | 1. By the end of the project, the level of climate risk management skills and natural resource conservation activities at the project sites to have increased by more than 50%. | Household surveys Project reports Workshop reports | Limited level of awareness among the communities There is adequate financial resources Sustained Government support for the project |
| Outcome 1: Enhanced capacity of national and regional stakeholders to plan, manage and implement climate change adaptation measures | Percent change in stakeholders’ use of climate risk assessment methods for design and/or decision-making on agriculture-related investments, assessed by survey. Establishment of District climate risk management institutional framework/process. Evaluation of the value of indigenous knowledge in climate risk management relative to meteorological information, as well as good practice measures- both traditional and innovative that are adaptive. |  | By the end of the project, more than 50% of the community, extension workers, and development partners to be using climate information for decision making. Climate risk management framework/protocols/coordination mechanism in place. Dissemination of information on the adaptive value of indigenous knowledge and adaptation practices as well as adaptation innovations to networks and policy-makers. |  |  |
| Outputs | 1.1 Availability of skills and tools necessary to continue CC risk assessments after the conclusion of the project, assessed by survey. 1.2 Percent change in stakeholders’ use of climate risk assessment methods for design and/or decision-making on agriculture-related investments, assessed by survey. 1.3 Evaluation of utility of meteorological information for agricultural decision-making. 1.4 Documentation and evaluation of indigenous knowledge system on climate risk management. 1.5Establishmentof District climate risk management institutional framework/process. 1.6 Development outreach programme and materials. 1.7.Level of Community awareness on policies and institutions supporting drought preparedness 1.8Documentation of good practices and success stories that are adaptive. | 1.1Very little application of climate and early warning information by both farmers and extension personnel 1.2 No documentation of indigenous knowledge on climate risk management. 1.3. No institutional framework on climate risk management at district or community level 1.4.Supportive policies and institutions on climate risk management are non existent 1.5 No documented knowledge on the adaptive value of existing technologies/ management regimes. | 1.1 Climate risk management tools developed e.g., an integrated early warning database systems that support vulnerability/CC risk mapping. 1.2 By the end of the project, more than 50% of the community, extension workers, and development partners to be using climate information for decision making. 1.3 Climate risk management framework/protocols/coordination mechanism in place. 1.4. By the end of the project, at least 50% of the farmers and pastoralist will be aware of the relevant policies and institutions dealing with climate risk management 1.5 Evaluation reports on the adaptive value of indigenous knowledge and adaptation practices as well as innovations. | Annual project field surveys Evaluation of relevant policies Official Government of Kenya reports Interviews and Questionnaires Project reports | Sustained financial resources. Sustained training of Ministry of Agriculture extension staff and effective and routine application of the acquired skill Political will from the Government in reviewing policies and procedures Institutional willingness to carry out policy reviews |
| Outcome 2: Enhanced capacity of district and local level stakeholders to plan, manage and implement climate change adaptation measures | Percent change in stakeholders’ capacities to make agriculture/pastoralism decisions based on climate information, assessed by survey. |  | By the end of the project, more than 90% of extension staff and, NGOs and private organizations working with the communities have skills in effective climate risk management practices |  |  |
| Outputs | 1. Trained extension officers in climate risk management practices 2. Percent change in stakeholders’ capacities to make agriculture/pastoralism decisions based on climate information, assessed by survey. | 1. Extension officers have very limited knowledge of effective climate risk management practices | 1. By the end of the project, more than 90% of extension staff and, NGOs and private organizations working with the communities have skills in effective climate risk management practices | Training materials Training event participation lists and evaluation reports | Training in pitched at the right level and well attended. |
| Outcome 3: Enhanced communities’ ability to plan, manage and implement climate-related activities | Percent change in farmers/pastoralists use of climate-resilient methods for managing climate change risks, assessed via survey. |  |  |  |  |
| Outputs | 3.1. Technical and financial feasibility assessments of proposed interventions 3.2 Percent change in farmers/pastoralists use of climate-resilient methods for managing climate change risks, assessed via survey. 3.3. Agricultural and pastoral productivity increased. | 3.1. Less than 20% of households are food insecure in 2005 3.2. Poor agricultural yields | 3.1. By the end of the project, at least 75% of the households are food secure within the pilot sites 3.2. By the end of the project, the yields among small-scale farmers will be increased by 10%, and livestock productivity increased by 10%. | Annual household surveys Annual monitoring and evaluation reports National Economic Surveys and other reports Annual MoA and livestock production reports | Sustained technical input from development partners Droughts still recur |

# SECTION III: Total Budget and Workplan

| Award ID: | 00047603 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Award Title: | PIMS 3792 Kenya: Adaptation to Climate Change in Arid and Semi-Arid Lands |  |  |  |  |  |  |  |  |  |  |  |
| Project ID: | 00057371 |  |  |  |  |  |  |  |  |  |  |  |
| Business Unit: | KEN10 |  |  |  |  |  |  |  |  |  |  |  |
| Project Title: | PIMS 3792 Kenya: Adaptation to Climate Change in Arid and Semi-Arid Lands |  |  |  |  |  |  |  |  |  |  |  |
| Implementing Partner (Executing Agency) | NEX : Kenya UNDP-CO |  |  |  |  |  |  |  |  |  |  |  |
| GEF Outcome/Atlas Activity | Responsible Party/ | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) |  | Total (USD) | Budget Notes |
|  | Implementing Agent |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 1: | GEF | 62180 | SCCF | 72100 | Contractual Services | 13,500 |  |  |  |  | 13,500 | 1 |
| Enhanced capacity of national and regional stakeholders to plan, manage and implement climate change adaptation measures |  |  |  | 71200 | International Consultant | 30,000 | 30,000 | 30,000 |  |  | 90,000 | 2 |
|  |  |  |  | 71300 | Local Consultant | 30,000 | 30,000 | 30,000 | 54,000 |  | 144,000 | 3 |
|  |  |  |  | 74500 | Training |  | 20,000 | 20,000 | 20,000 |  | 60,000 | 4 |
|  |  |  |  | 71600 | Travel | 5,000 | 6,000 | 6,000 | 3,000 |  | 20,000 | 5 |
|  |  |  |  |  | sub-total GEF | 78,500 | 86,000 | 86,000 | 77,000 |  | 327,500 |  |
| OUTCOME 2: | GEF | 62180 | SCCF | 71200 | International Consultants |  | 15,000 |  | 15,000 |  | 30,000 | 6 |
| Enhanced capacity of district and local level stakeholders to plan, manage and implement climate change adaptation measures |  |  |  | 71300 | Local Consultants |  | 25,000 | 25,000 | 7,600 |  | 57,600 | 7 |
|  |  |  |  | 72100 | Contractual services |  | 26,200 | 26,200 |  |  | 52,400 | 8 |
|  |  |  |  | 71400 | Travel |  | 20,000 | 20,000 | 20,000 |  | 60,000 | 9 |
|  |  |  |  |  | sub-total GEF |  | 86,200 | 71,200 | 42,600 |  | 200,000 |  |
| OUTCOME 3: | GEF | 62180 | SCCF | 71200 | International Consultants |  | 0 | 30,000 | 30,000 |  | 60,000 | 10 |
| Enhanced communities’ ability to plan, manage and implement climate-related activities |  |  |  | 71300 | Local Consultants |  |  | 48,000 | 48,000 |  | 96,000 | 11 |
|  |  |  |  | 71600 | Travel |  |  | 20,000 | 20,000 |  | 40,000 | 12 |
|  |  |  |  | 72100 | Contractual Services |  |  | 89,500 | 80,000 |  | 169,500 | 13 |
|  |  |  |  | 72300 | Materials and Goods |  |  | 44,000 |  |  | 44,000 | 14 |
|  |  |  |  |  | sub-total GEF |  |  | 231,500 | 178,000 |  | 409,500 |  |
| Project MANAGEMENT UNIT | GEF | 62180 | SCCF | 71600 | Project Secretariat | 4,000 | 4,000 | 4,000 | 8,000 |  | 20,000 | 15 |
|  |  |  |  | 71300 | Local Consultants | 5,000 | 5,000 | 5,000 | 10,000 |  | 25,000 | 16 |
|  |  |  |  | 71600 | Travel |  | 5,000 | 8,000 | 5,000 |  | 18,000 | 17 |
|  |  |  |  |  | sub-total | 9,000 | 14,000 | 17,000 | 23,000 |  | 63,000 |  |
|  |  |  |  |  | Project Total | 87,500 | 186,200 | 405,700 | 320,600 |  | 1,000,000 |  |
| Summary of Funds: [1] |  |  |  |  |  | Year 1 | Year 2 | Year 3 | Year 4 |  | Total |  |
| GEF |  |  |  |  |  | 87,500 | 186,200 | 405,700 | 320,600 |  | 1,000,000 |  |
| Office of the Prime Minister-Arid Land Resource Management Project |  |  |  |  |  | 203,066 | 203,066 | 203,066 | 203,065 |  | 812,263 |  |
| Government of Kenya - Ministry of Agriculture |  |  |  |  |  | 75,000 | 75,000 | 75,000 | 75,000 |  | 300,000 |  |
| Government of Kenya - Meteorological Department |  |  |  |  |  | 61,170 | 61,170 | 61,170 | 61,171 |  | 244,681 |  |
| TOTAL |  |  |  |  |  | 426,736 | 525,436 | 744,936 | 659,836 |  | 2,356,944 |  |

Budget Notes

Budget Note 1:  This estimate is for the contribution of the UNDP component to the wider KACCAL project of cost of conducting an inception meeting including covering miscellaneous organizational costs.

Budget Note 2: 60 days/annum over three years at a rate of $500 per day is estimated for an international consultant to develop tools and methodologies for integrating climate change risk reduction measures into community and national development plans, developing knowledge platforms, an advocacy and outreach plan, inputs into a drought preparedness plan and for developing the strategy for the adaptation learning component. Draft terms of reference are attached and will be refined by the project manager and approved by the Project Board prior to contracting.

Budget Note 3: The cost of national consultants to support the achievement of outcome 1 is estimated at 150 days/annum over four years at a rate of $240 per day. Key tasks include developing tools and methodologies for integrating climate change risk reduction measures into community and national development plans including developing climate change resilient drought/flood mitigation and preparedness plans, developing knowledge platforms, an advocacy and outreach plan and for developing and developing and implementing a monitoring and evaluation plan. Detailed terms of reference must be outlined by the project manager and approved by the Project Board prior to contracting.

Budget Note 4:  This reflects the amount of money available each year to cover the costs of training (including organization costs for technical support) for the use of climate risk information for planning purposes at the national and regional level, for the implementation of an integrated drought management system and the implementation of an outreach programme and stakeholder coordination.

Budget Note 5:  A rate of US$0.50 per kilometer for 22,000 km (in total) is used for all project related travel within the country in support of Outcome 1 (including learning tours of farmers and policy makers visiting pilot sites and other drought affected sites within Kenya, facilitation of collaborative working between stakeholders) as well as $9k for travel for the international consultants (1 trip per year for 3 years).

Budget Note 6.  A rate of $500 per day for 30 days/annum over two years is estimated for support for activities related to capacity strengthening at district and local levels.

Budget Note 7: This is estimated at a rate of $240 for 80 days/annum over three years for local consultant(s) support over the project lifetime for the achievement of outcome 2: capacity strengthening at district and local levels.  This amount includes the cost of preparing and publishing relevant materials in support of outcome 2.

Budget Note 8:  This covers the cost of holding training events.

Budget Note 9: This covers the cost over four years of getting people to training events, consultations and meetings.

Budget Note 10: This estimate is based on a rate of $500 per day for 60 days/annum over two years to help develop technical and financial feasibility assessments and technical guidance in support of outcome 3:  Community-Based Micro-Projects Supported.

Budget Note 11: This estimate is based on a rate of $240 per day for 200 days/annum over two years for a project manager and technical support staff to support the achievement of outcome 3: Community-Based Micro-Projects Supported.

Budget Note 12:  This estimate is based on rate of US$0.50 per km for 50,000 km of all project related travel within the country related to outcome 3 e.g. getting people to consultation meetings and consultants to the project site, and $15K of travel expenses for the international consultants.

Budget Note 13: This estimate is made for community groups to carry out pilot demonstration activities as outlined in the approved project document.

Budget Note 14: This estimate is to account for materials that might be needed to implement the adaptation measures such as seeds, tools and construction materials.

Budget Note 15:  This amount will support the marginal costs of UNDP’s use of the project secretariat, which will be coordinated by ALRMP (OP) and shared by the joint WB-UNDP project.

Budget Note 16: At a rate of US$250 per day, this will cover the cost of 25 days/annum over four years of purely management related activities by a national consultant. This will include organizational duties, issuance of terms of reference and other administrative functions related to the effective implementation of the project.

Budget Note 17: This will cover the costs of travel within Kenya related to project management only. Costing is based on an estimate of US$0.5 per kilometer of travel.

# SECTION IV: ADDITIONAL INFORMATION

# PART I: Other agreements

Endorsement letters from the Government of Kenya are attached to this project document.

## PAR

PART II: Organigram of Project

Please refer to the text in the section on Management Arrangements

PART III: Terms of References for key project staff and main sub-contracts

See Annex 1

# PART IV: Stakeholder Involvement Plan

See annex 3

# PART V to X: Other additional information

(As required by the specific focal area, operational program, and strategic priority)

See Annex 4 for UNDP Template for Lessons Learned on Adaptation projects.

# Annexes

Annex 1: Terms of Reference

Annex 2: Terms of Reference for the Regional Component of the UNDP Coping with Drought and Climate Change Project in Kenya, Ethiopia, Zimbabwe, and Mozambique

Annex 3: Stakeholder Involvement Plan

Annex 4: UNDP Template for lessons learned in adaptation projects

Annex 5: Minutes from CwD Project Stakeholders’ Workshop

Annex 6: Maps

Annex 7: Photographs from Pilot sites

# Annex 1: Terms of References (TORs)

To be finalized prior to the inception meeting of this project by the Implementing Partner in consultation with UNDP CO and RTA. [Co-management arrangements with the WB-supported KACCAL project will be explored during the project start-up phase].

Background

(This background is common for all Terms of References but changes can be made according to specific goals for each TOR)

The Initial National Communication (INC) indicates that impacts of climate change are particularly serious for Kenya, where the effects of the doubling of the current concentration of CO2 in the atmosphere is likely to increase the mean air temperature, reduce rainfall in ASALs, increase the solar radiation and increase the evapo-transpiration.  Very recent and past droughts are known to have had devastating environmental and socio-economic impacts on the country, particularly in ASALs.

This UNDP-managed component of the joint UNDP-WB KACCAL project seeks to develop and pilot a range of coping mechanisms for reducing the vulnerability of small-holder farmers and pastoralists in pilot districts in Kenya to future climate shocks.  Drought prone Mwingi District was selected as a pilot site for the UNDP-managed component of the joint UNDP-WB KACCAL project.  The project is structured around three outcomes, as described in the logical framework matrix (Annex 1).

Objective

This assignment aims at ensuring effective and timely implementation of the project activities, provision of administrative and technical assistance required by the Reference Group and other parties involved in the project, and coordinate any activities taking place in the project site.

### 3.1 Terms of References for the National Project Manager (PM)

Tasks and Responsibilities

The National Project Manager (PM) will ensure effective and timely implementation of the UNDP-managed component of the joint UNDP-WB KACCAL project, provide administrative and technical assistance required by the project implanting partners and other parties involved in the project, and coordinate any activities taking place in the project site.

The PM will liaise with the project national steering committee (which includes all major national stakeholders), the Ministry of Agriculture (MoA)-led district steering committee, and the UNDP Country Office.  The PM will work under the supervision and guidance of the UNDP-CO project representative and together with other PM forms part of a team.  Frequent communication with the other team members is expected from the PM.  The activities for which the PM is responsible include:

- Provide strategic guidance to the Project Steering Committees.

- Develop a collaborative planning framework for all phases of project management and delivery.

- Ensure effective project implementation in line with the Project Documents including the workplan.

- In coordination with UNDP country Office ensure delivery and disbursement of UNDP funds, in order to achieve the stated Projects’ Outputs and Outcomes

- Develop project workplans for undertaking the KACCAL project activities.

- Ensure the timely implementation of planned activities as identified in the workplan.

- Develop Terms of Reference for procurement of technical services.

- Supervise and review the work done by indicated technicians and consultants.

- Define assessment methodologies according to the GEF guidelines for the planned capacity stocktaking work at the project site.

- Ensure UNDP manuals and procedures and financial rules and regulations are followed.

- In coordination with UNDP country Office, and in accordance with project document guidance’s, ensure preparation and delivery of the following project reports:

  - Inception Report, Quarterly Financial Reports, Bi-annual Progress Reports, Annual Project Report, Project Implementation Review, Occasional Status Reports and Briefing Notes, Technical Reports, Project Publications, Project Terminal Report.

- Review existing capacity assessment literature compiled in preparation of CBD, UNFCCC and UNCCD national communication.

- Prepare briefing documents, develop and update information materials to ensure that stakeholders have a common understanding of the project.

- Monitor and evaluate the implementation of the project every six months, and report to the PM through the Reference Group.

- Organize meetings on behalf of the project team including stakeholder meetings.

- Organize meetings with the central, provincial and district project steering committees at regular basis to evaluate the project progress.

- Monitor other regional and national environmental projects (GEF or non-GEF), and streamline the UNDP Projects’ activities with these initiatives.

- Perform any other duty relevant to the assignment

Output

- Project Document outcomes, work plan, budget and terms of reference of project staff and project management structures taking into account the prodoc logframe

Qualifications and Experience

A Bachelor’s degree in a field related to environmental management, agricultural science, meteorology and other related sciences.  Experience in drought management issues at the farm and policy level.  Knowledge of climate change, drought preparedness and mitigation and biodiversity issues.  Familiarity with GEF guidelines/procedures including logical framework, project development/management.  A good understanding of development and environmental/agriculture or climate issues in Kenya.  Familiarity with the UN Convention on Biological Diversity, the UN Convention to Combat drought and desertification, and the UN Framework Convention on Climate Change.  At least 5 years of work experience (including in project management).

Skills:

- Leadership skills;

- Team player;

- Diplomatic and negotiation skills;

- Sensitive to government and civil society interactions;

- Advanced reporting skills;

- Strong managerial and administrative background, especially in accounting, procurement, disbursement, monitoring & evaluation;

- Conversant and at pace with funding opportunities;

- Trouble shooter and problem solver;

- Pro-active, adaptive management skills;

- Strong economics / financial background;

- Project identification and development skills

- Ability to establish priorities and to plan and coordinate work;

- Ability to effectively coordinate a multi-stakeholder project;

- Excellent communication skills;

- Ability to lead, manage and motivate teams of international & local consultants and other stakeholders to achieve results;

- Committed to and diligently working towards achieving results for sustainable change;

- Fully Computer literate.

Duration of assignment

The total duration of this assignment is 5 (five) years during which the consultant will work 5 (five) working days over a period of one week.  The PM will work under the guidance of the UNDP-CO project representative and report directly to the UNDP Country Office, Project focal point at the Government of Kenya and steering Committee.

### 3.2 Terms of reference of the District Project Steering Committee

Introduction

This steering committee is intended to serve the UNDP-managed component of the joint UNDP-WB KACCAL project, in the UNDP pilot site in the Mwingi district.  To succeed in this project and especially to build a national consensus, a Climate Change Adaptation Road Map for the project area will be instrumental in identifying the social and technical systems needed and climate change related challenges that the agricultural sector, and rural agro-pastoralists in semi-arid regions will be facing in the next ten years.  Government, Non-governmental, private and international development agencies have been recognized as vital key strategic partners for this project.  It is the desire that these players unite their efforts in bringing fruition to this project.  These core organizations shall work closely together as part of a steering committee responsible for providing overall guidance on this project.

The project proposal provides a detailed background to the Project, and a project plan has been developed to support implementation of the project.

Role of the Steering Committee

- Take responsibility for the achievement of outcomes for the UNDP-managed component of the joint UNDP-WB KACCAL project;

- Address any issue (s) that has major implications to the project;

- Provide overall direction and advice to the Project Manager;

- Sign off on relevant aspects of the project;

- Represent various interests of stakeholders and facilitate strategic alliances with these sections.

District Project Steering Committee Functions

The Project Steering Committee will:

- Provide input to the membership of any other Working Groups, as required;

- Guide the preparation of the final product prepared by the Project Manager;

- Approve the contents of the documents released to the public and Government authorities, as required;

- Provide input on a potential strategy for the implementation, as appropriate, of some or all recommendations generated by the UNDP-managed component of the joint UNDP-WB KACCAL project;

- Act as liaison between the Project Steering Committee and their own professional organization;

Composition

- Each partner organization will have the privilege of self-appointing one representative who will participate in all the activities of the Steering Committee.

- The Project Steering Committee will be comprised by representatives from the government, NGOs, International Development Partners, Private Sector, Project manager and the secretariat representative.

Membership Rotation

Appointments will be for the duration of the project.  While it is not expected that rotation will be required, circumstances may arise when a member of the Steering Committee may need to be replaced.  The represented organization will be responsible for the new appointment and will ensure continuity in the representation.

Communication with the Public

- All inquiries with respect to this project shall be channelled through the co-Chairs of the Project Steering Committee or through the Project Manager's Office.

- All correspondence with the public which could be interpreted as reflecting the views of the Committee shall be signed by the co-Chairs, the appointed Project Manager or other persons authorized by the co-Chairs.

- Only the co-Chairs and the Project Manager or other persons designated by the Chair, are authorized to speak on behalf of the Steering Committee.

- Requests from the public for general explanations of the project process/ documents will be responded to by the Project Manager's Office staff directly involved with the project.  Such explanations shall be confined to information only.

Secretarial Support

- The Project Manager will provide secretarial support for the Project Steering Committee.

- The Project Manager, will act as Secretary to the Committee.  Secretarial support will be provided for the organization of meetings, preparation of the agenda in co-operation with the Project Steering Committee co-Chairs, preparation of meeting minutes and informing the Project Steering Committee members of project developments through regular communications channels.

- The Project Manager will be responsible for reporting to the Project Steering Committee on all issues pertinent to the management of the project.

Travel Expenses

Each organization represented on the Steering Committee is responsible for the travel expenses of its representative, unless specifically requested in writing by the project, in which case the project travel guidelines will apply.

Attendance and Participation at Meetings

- Attendance and participation at meetings of the Committee by non-members shall be at the discretion of the co-Chairs.

- Members of the public intending to attend a committee meeting shall notify the Committee Chair of such intent.

- Participation in Committee discussions shall normally be limited to Committee members and assigned staff.  Invited guests and other members of the public may participate with the approval of the co-Chairs.

- Committee members are not permitted to name alternates.

Communication guidelines

All formal communications between members of the Steering Committee will be copied to other members.

Project documents that will be supplied to members

- Project Proposal

- Steering Committee Terms of reference

- Communication strategy

- Project plan

- Status reports

- Agendas and minutes from meetings

### 3.3 Terms of Reference for National Consultants

This TORs is only indicative.  Specific and more detailed TORs will be developed in the project inception workshop or during the project lifetime according to the requirements of each consultancy (contractual service).

The indicative tasks of the local consultants include:

- Establish an internet based information delivery system;

- Conduct training on forecasting climate change and climate variability;

- Develop educational materials for training;

- Assist in the establishment of an early warning system;

- Production of educational materials for training of project staff;

- Develop tools for mainstreaming of climate change into development plans and provide training on the method of preparation of mitigation plan;

- Undertake specific technical tasks to address project activities as per indication of the Project Management Unit.

### 3.4 Terms of Reference for the International consultant

This TORs is only indicative.  Specific and more detailed TORs will be developed in the project inception workshop or during the project lifetime according to the requirements of each consultancy (contractual service).

The indicative tasks of the international consultants include:

- Establish drought information system and data base establishment in the pilot area;

- Organize training to build the capacity of relevant stakeholders to use climate change information;

- Design risk management system and prepare educational materials for risk management;

- Organize training on the promotion of integrated climate risk management;

- Assist in the preparation of community based drought mitigation plan;

- Conduct marketing survey to identify the potential to market dry land products from the pilot areas;

- Undertake specific technical tasks to address project activities as per indication of the Project Management Unit.

# Annex 2: Terms of Reference for the Regional Component of the UNDP Coping with Drought and Climate Change Project in Kenya, Ethiopia, Zimbabwe and Mozambique

- UNDP’s Coping with Drought Project was initially pipelined at the GEF as a Full Size Regional Project for East and Southern Africa.  The regional dimension of the project was motivated by a number of factors including:

- The management of climate information in East and Southern Africa takes place in a regional manner.  Regional climate outlook fora gather, analyze, forecast and disseminate climate information along a chain of regional, national and local users.

- All four countries expressed their interest in this work by participating in a farmer-focused survey on accessibility and use of contemporary and indigenous climate information conducted in 1999.  Since then through regular consultations between UNDP-DDC, UNDP and the countries possible interventions on drought mitigation and climate adaptation have been identified.  In all four countries activities in the context of drought management have been initiated between UNDP and the respective governments.

- Given the correlation between ENSO (El Nino/ Southern Oscillation), rainfall, drought, and food insecurity, ENSO based climate predictions are similar in general terms but different at specific sites for each of the four countries.  The usefulness of ENSO predictions to reduce risks in agricultural production associated with rainfall variability can be tested across Eastern and Southern Africa.  Furthermore, the regional approach allows comparing the effectiveness of different response measures.

- Similarities with regard to drought vulnerabilities across all four countries, and to a certain extent similarities of response measures, allow sharing of knowledge and horizontal learning between countries.  Knowledge sharing and learning will be facilitated by a regional approach and specific activities identified during the preparatory phase.

- The need for technical input on a demand-driven basis from specialized agencies such as the Drylands Development Centre, and others including WMO, NOAA, IRI, and NDMC.

2.  For a number of logistical and programming reasons, the regional project was subsequently submitted as four separate Medium Sized Projects to GEF Council.  However, the regional dimension of the GEF pipelined project was retained through the specification of an outcome that focused on the regional dimension of the project in each of the separate MSPs.

3.  Discussions during the preparatory phase converged to the identification of the Drylands Development Centre (DDC) as the lead for the regional component of the project.  DDC is a centre of excellence dedicated to working with people to fight poverty in the drylands of the world.  The Centre helps to influence policies through research and analysis of drylands policies, providing advice, and policy-making support to decision-makers, designing and managing capacity development programmes in drylands, and working towards ensuring that national policy and planning frameworks address the social and environmental concerns of dryland populations.  DDC has expertise in building partnerships, generating knowledge and promote learning.  DDC also promotes the strengthening of the capacities of individuals and institutions at the local level while working to ensure that national policy and legislation support local development.

4.  These Terms of Reference outlines the regional component of the Coping with Drought initiative.

Outcome 1: Strengthened knowledge base, coordination, and information sharing towards action on management of climatic risk at the National and Regional levels.

Activities to achieve this outcome will be anchored on establishing regional applied knowledge exchange mechanism for climate change adaptation practices established.  This will be achieved in synergy with the African Drought and Development practitioners’ Network, for the benefit of project countries, as well as a basis for potential wider replication of successful approaches to building adaptive capacity.

(a) 	Key lessons, good practices and methodologies are supplied from projects and other sources (as inputs to Outcomes 1-3 in each national project) in a systematic manner, through applied knowledge products.

(b)	Capacity building activities facilitated (related to Outcomes 1-3), including for methodology development for indicators of adaptive capacity, as a basis for identifying successful approaches

(c)	Lessons, practices and methodologies applied, as inputs into Outcomes 1-3 at national level.

(d) 	Coordination functions maintained (a) between country projects and (b) between the set of country projects and external parties and potential partners, in part through development of a Coping with Drought ‘brand’

# Annex 3: Stakeholder Involvement Plan

Local and national stakeholders will be heavily involved in the UNDP component of the joint UNDP-WB KACCAL project, through community-based activities, national consultations, and co-management of project outcomes.  Stakeholder involvement is crucial, in order to ensure buy-in and effective delivery of results of local, vulnerable populations.  The will be ensured by engaging with community and with national government through a cross-scale approach, involving communities in activities and disseminating lessons and engaging in policy dialogue with government stakeholders.  Stakeholders at all levels were also involved in the formulation of the UNDP component of the joint UNDP-WB KACCAL project during the project preparatory phase.  A meeting was held during 2005, and the topics discussed, groups involved, and main messages are described below.

List of Stakeholders and Areas of Participation

| Name of Stakeholder | Area of Participation |
| --- | --- |
| (a) Non-Governmental Organizations (NGOs) in Mwingi |  |
| Mitamisyi Poverty Alleviation Programme (MPAP) | -acquisition of oxen and ploughs. -Support to groups to start incomes generating activities like vegetable Production and purchase of goats. |
| World Vision Kenya | -Support farmers training on food security -Support trainings for community resources (persons) like soil conservation Assistants. -Subsidizing farm inputs, e.g. Improved seedlings and livestock breeds. |
| Mwingi Farmers Field School Networks | -Marketing farm produce jointly for registered groups, with emphasis on green grams and sorghum collectively. -Experience sharing among themselves and with experts -Have collective bargaining for better prices and ensure farmer empowerment in decision making process on matters that affect them -Accessing information about their farming activities -Share costs while undertaking joint activities such as collective farm input procurement. |
| Kitui Ginneries Ltd | -Purchase of cotton -Availing cotton seed. |
| Catholic Diocese of Kitui (CDK) | -Capacity building for groups -Availing seeds at subsidized prices |
| KARI – Katumani | -Sorghum trials and fertility improvement trials -Tomato variety trials |
| Genesis | -Provision of seed -Capacity building for groups -Provision of pesticides to farmers on loan basis. |
| AAK Tharaka DI | -Capacity building groups -Provision of inputs to groups undertaking vegetable production (Drip kits, vegetable Seed) |
| Mwingi District Community Based Seed Bulking & Stockists Association (DISCOBSA) | -Availing seed to seed bulking farmers. |
| NGOCAP | Provision of ox-ploughs to farmers |
| Farm Africa | -Relief -environmental conservation |
| Action Aid | -Relief |
| Christian Children Fund |  |
| Organization of Sustainable Capacity for Development (OSCAD) | -environmental conservation -food security |
| (b) Community Based Organizations (CBOs) in Mwingi District |  |
| Mutanda Community Based Organization (MUCOBO) | Environmental Conservation |
| Mumoni- Kyuso community Based organization (MUKY) | -Environmental Conservation |
| (c) Farmer Organizations in Mwingi District |  |
| Farmer Field schools (FFS) Soil Conservation assistants Farmer Innovation Networks Beekeepers Association Horticultural growers Ranches Para-Veterinary Assistants |  |
| (d) Government Departments |  |
| Arid Lands Resources Management Programme (ALRMP) National Environment Management Authority (NEMA) Kenya Meteorological Department (KMD) Department of Resource Survey and Remote Sensing (DRSRS) Forest Department Water Department Livestock Production Department Crop production Department Fisheries Department Culture and Social services Co-operative Development Department District Development Committee Veterinary Services Department |  |
| (e) International Organizations |  |
| United Nations development Programme (UNDP) Food and Agricultural Organization (FAO) Famine early warning system Network (FEWS-NET) IGAD Climate Prediction and Application Centre (ICPAC) |  |

# Annex 4: UNDP Template for lessons learned in adaptation projects

(To be adapted under guidance by UNDP’s Regional Technical Advisor on Adaptation)

Completed by: 							Date:

Project Data

Name of the project:

PIMS:

Motives – engaging stakeholders

1.  What development challenge(s) motivated this project?

2.  What climate-related challenge(s) motivated this project?

Baseline activities and additionality

3.  What were the successes and challenges of building on baseline development to design the project?  What makes the activities funded by the project “additional” (attributable to climate change)?

Inputs/Gaps in resources for project development

4.  What were the most useful sources of climate change and other information utilized in project design?  What information gaps arose?

5.  How useful was Adaptation Programming Website in developing the project and how could it be improved?

Factors for success/failure

6.  What key factors hindered timely progress in project development, and what key factors enabled success?  (e.g.  Methods, policies, capacities, etc.)

Methods: Project problem analysis

7.  Describe the challenges and benefits of the methodologies used for problem analysis, e.g.  For baseline assessment; APF approaches; use of GCMs or climate observations; outcomes or processes from assessments (NAPAs, NCs), etc.

Methods: Assessment of adaptation response

8.  Describe the challenges and benefits of the methodology used for identification and selection of adaptation responses (e.g.  Assessment of current coping/adaptation; assessment of maladaptation; cost-benefit analysis; multi-criteria analysis, etc.)

Other Adaptation priorities identified

9.  What key systems or areas were identified as priorities for adaptation during project development that will NOT be addressed by the project?

Overall

10.  Recommendations for future adaptation project developers.

1.

2.

3.

# Annex 5: Minutes from CwD Project Stakeholders’ Workshop

Mwingi Tourist Hotel, Mwingi Town, 14th – 15th November 2005.

Day one 							14th November 2005

Programme:

08.00 – 08.45	Arrival and Registration of Participants – Mwingi Tourist Hotel

Chair: D.M. Kang’esa -DAO -Mwingi

Rapporteurs: C.Oludhe and A.Oroda

08.45 – 09.00	Prayer and Introductions

09.00 – 09.30	Opening Remarks

- UNDP CO Representative		- Charles Nyandiga

- UNDP Regional Project Manager	-Pradeep Kurukulasuriya

- MoA Project Coordinator		-Isaiah Gitonga

  - – 11.00	Session two –Presentations

09.30 – 09.45	Project Overview and site selection	- Fred Karanja, NC

09.45 – 10.00	District Resource Degradation		- H.K.  Kiema, DLPO, Mwingi

10.00 – 10.15	NEMA Activities in Mwingi		- P.  Wambua, DEO, Mwingi

10.15 – 11.00	Discussions

11.00 – 11.20	Coffee/Tea Break

11.20 – 11.30   FFS Activities in the District	- Mr.  Mwanga, DFFS Coordinator

11.30 – 11.40   Farmer Presentation		- Kalamba Muyo FFS

11.40 – 11.50   Farmer Presentation		 - Kaghui FFS

11.50 – 13.00   Discussions

13.00 – 14.00	LUNCH	-Mwingi Tourist Hotel

14.00 - 15.40	Group Discussions	Chair: 	Isaiah Gitonga

-Adaptive capacity assessment (challenges of coping with drought)

-Identification of potential coping mechanisms

-Assessment of existing early warning system (problems and ways to improve)

15.40 – 16.00	Coffee/Tea Break

16.00 – 17.00	Recommendations and way forward

_____________________________________________________________________

Day two						15th November, 2005

Field Trip

06.30 – 07.00	Assemble at MoA Offices, Mwingi

07.00 - 09.00	Traveling to Kamuwongo Farmer’s Field School

09.00 – 12.00	Field visit and Discussions

12.00		Closing and traveling back to Mwingi Town

______________________________________________________________________________

List of Participants

| Serial No. | NAME | ORGANIZATION | ADDRESS |
| --- | --- | --- | --- |
| 1 | Mrs. Patricia M. Wambua | National Environment Management Authority (NEMA) | P.O. Box 30, Mwingi Tel: 0735-593702, 0723372468 patriciamukua@yahoo.com |
| 2 | Mrs. Janice M. Mwinzi | Mwingi District water Office | P.O. Box 19, Mwingi Tel: 0735-948791 |
| 3 | Charlwes Mugo Njine | Ministry of Agriculture | P.O. Box 31, Mwingi. Tel: 0733360358 |
| 4 | Mr. Symon C. J. Mburia | Ministry of Cooperative Development | P.O. Box 248, Mwingi Te: 044-822241, 0721743259 |
| 5 | Mr. Julius Mutie Kivinduko | Ithingili Farmers field school | P.O. Box 34, Kamuwongo |
| 6 | Mr. John N.T. Miru | District Social Development office-Mwingi | P.O. Box 137, Mwingi Tel: 0735195081 |
| 7 | Mr. Patrick Mutugi Kirimi | Ministry of Agriculture | P.O. Box 31, Mwingi Tel: o44-822378, 0734926532 |
| 8 | Mr. Mutuku Ndunda | Ministry of Livestock & Fisheries Development | P.O. Box 31 Mwingi Tel: 0734553398 |
| 9 | Mr. D.M. Kangesa | Ministry of Agriculture | P.O. Box 31, Mwingi Tel: 044-822378 |
| 10 | Mr. Jacob Wambua Mwova | Kaghui Farmers Field School | P.O. Box 17, Kyuso, Mwingi |
| 11 | Mrs. Mawia Musyoka | Kaghui Farmers Field School | P.O. Box 17, Kyuso, Mwingi |
| 12 | Mr. Samwel Njenga | World Vision | P.O. Box 390, Mwingi Tel: 0723510935 samwelirari@yahoo.com |
| 13 | Mr. James Angwenyi Nyangaka | Ministry of livestock & Fisheries | P.O. Box 416, Mwingi Tel: 044-822139, 0735419779 |
| 14 | Mr. Job M. Mwinzi | MUKY-ORDAP | P.O. Box 672, Mwingi Tel: 0724930198 |
| 15 | Mrs. Ruth M. Samwel | MUCOBO Community Based Organization | P.O. Box Katse Tel: 0724930174 |
| 16 | Mrs. Kasyoka Kimwele Nzuu | Kalamba Muyo Farmers Field School | P.O. Box Kamuwongo |
| 17 | Mrs. Stellah Syungu Kyalo | Kalamba Muyo Farmers Field School | P.O. Box Kamuwongo |
| 18 | Mr. Solomon Mutemi Mukiti | Kalamba Muyo Farmers Field School | P.O. Box Kamuwongo |
| 19 | Mrs. Mary M. Mwanzau | Ministry of Agriculture | P.O. Box 31, Mwingi Tel: 0733452341 |
| 20 | Mr. Titus Muthini Utungu | Ministry of Agriculture | P.O. Box 31, Mwingi Tel: 044-822378, 0733413419 |
| 21 | Mr. H. Kitonga Kiema | Ministry of Livestock & Fisheries | P.O. Box 31, Mwingi Tel: 0735648915, 0722694435 |
| 22 | Mrs. Esther Muhanjya | Ithinguli Farmers Field School | P.O. Box 34, Kamuwongo, Mwingi |
| 23 | Mr. Daniel Kimanzi Mwanga | Ministry of Agriculture | P.O. Box 31, Mwingi Tel: 044-822378, 0735477425 |
| 24 | Mr. Charles Nyandiga | UNDP CO | P.O Box 30218 (00100), NAIROBI Tel: 624447 charles.nyandiga@undp.org |
| 25 | Mrs. Joy Kagwira Ochieng | Ministry of Agriculture | P.O. Box 31, Mwingi Tel: 044-822378, 0733455674 joisom@yahoo.com |
| 26 | Mr. Arthur Njeru Maathai | Ministry of Agriculture | P.O. Box 31, Mwingi Tel: 044-822378, 8222049, 0723707663 amaathai@yahoo.com |
| 27 | Dr. F.K. Karanja | UNDP National Consultant, University of Nairobi | P.O. Box 30197, NAIROBI, 00100 Tel: 067-21241, 0733780038 fkaranja@swiftkenya.com |
| 28 | Dr. I.I. Gitonga | Ministry of Agriculture, Project Coordinator | P.O Box 34097, NAIROBI Tel: 020-2713901 iimaita@yahoo.com |
| 29 | Dr. Pradeep Kurukulasuriya | UNDP, Project Manager | P.O. Box 305 E45th ST, NEW YORK, NY 10017 Tel: 718938 9965 pradeep.kurukulasuriya@undp.org |
| 30 | Mr. Antony M. Kavisi | Ministry of Agriculture | P.O. Box 31, Mwingi Tel: 044-822378, 0725973792 |
| 31 | Mr. Edward Njaramba Macharia | Ministry of Culture & Social Services | P.O. Box 317, Mwingi Tel: 0734588691 |
| 32 | Mr. A. Oroda | Kenyatta University | P.O. Box 61361, NAIROBI, 00200 Tel: 0722254862 Ambrose_oroda@yahoo.com |
| 33 | Dr. C. Oludhe | University of Nairobi | P.O. Box 30197, NAIROBI, 00100 Tel: 020-4449005, 0722866106 coludhe@uonbi.ac.ke |
| 34 | Mrs. Jacqueline Kiio | Ministry of Agriculture | P.O. Box 31, Mwingi Tel: 044-822378, 0720368148 jackiekiio@yahoo.com |
| 35 | Ms. Joyce Ruitiari | Ministry of Agriculture | P.O. Box 30028, NAIROBI Tel: 0722770383 Ruitiari@yahoo.com |
| 36 | Mr. C.B. Lukorito | University of Nairobi | P.O. Box 30197, NAIROBI, 00100 Tel: 020-4449005, 0734425294 cbusolo@uonbi.ac.ke |

Session one	- opening

Mr. D. Kang’esa, the Mwingi District Agricultural Officer (DAO), welcomed the  participants to the workshop and said that due to the varied social backgrounds  of the participants the workshop would be conducted in three languages – English, Kiswahili and Kikamba (for those not able to express themselves in English or Kiswahili, particularly the farmers).  He then asked the participant to introduce themselves.  After the introduction, the Chairman took the participants through the programme.

Summary of the DAO’s remarks

- Mwingi District is generally a hardship area where only one season out of four seasons experience successful cropping the rest experiencing crop failure.

- Water is scarce hence people spend a lot of time looking for water.

- There are plenty of diseases for both humans and livestock.

- Waterborne disease are generally common due to scarcity of water hence people cannot have clean drinking water.

Despite the numerous problems, people still live in Mwingi.  This is mainly because of the wealth of the indigenous knowledge that people have, particularly in:

- Soil conservation

- The use of drought tolerant crops

- Strict preservation of seeds

- Selection of indigenous crop seeds

It was noted that:

- Human and livestock diseases, including snake bites, are usually treated by use of herbs.  The traditional medicines should, therefore, be enhanced.

- There is indigenous knowledge used in forecasting rainfall

In conclusion the participants were informed that the Project team was interested in documenting   the local people’s views on the proposed project.  The team was in the process of carrying out an assessment that would enable the development of a project proposal to be funded by the UNDP, together with the GoK and other development partners.  The project is aimed at enhancing the local people’s ability to cope with droughts and the impacts of climate change.

Summary of Isaiah Gitonga’s remarks said that:

- Since independence there had been a lot of projects implemented in Kenya by the Ministry of Agriculture, NGO’s, International Organisations (such the Food and Agriculture Organisation of the United Nations), etc, particularly in the hardship areas but there was nothing to show for it.

- Why has there been no success in food self-sufficiency production?

- Farmers were challenged to give reasons, in their view, why this has been the case.

- Noted that top – down approach in project design and development is no longer being used, but bottom – up approach.  There is need to have the local people projects thought through from the ground as part of enhancing the success of projects

- There was interest in finding solutions to the persistent problems or hardships.

- Any projects being implemented should show success

- He concluded by encouraging the farmers to speak out the problems they usually face that hinder their development.

Pradeep Kurukulasuriya, the Regional Project Manager was introduced to the participants by the NC.

Session two - Presentations

Summary of Fred Karanja’s presentation

The presentation highlighted the following:

- The overview of the project

- Site selection (see Annex A)

Two sites corresponding to two administrative divisions in Mwingi District of Eastern Province of Kenya were selected for piloting and subsequent project implementation.  These are Mumoni and Kyuso divisions.

- Stakeholders input in the design of the project

Key components of the project are:

- Piloting coping strategies

- Improving early warning systems

- Implementation of drought preparedness mechanisms

Principal or important issues of the project were

- To build on what was existing with focus on land degradation and food security

- Coordination to avoid duplication

Summary of Kitonga Kiema’s presentation

Resource Degradation in Mwingi District

An overview of natural resource degradation in Mwingi District was presented.

i) Agro-ecological zones of Mwingi District and their land area coverage (Annex B)

| Agro-ecological Zone | Extent |
| --- | --- |
| UM 3 | 19.8 km2 |
| UM 4 | 114.9 km2 |
| LM 4 | 952.6 km2 |
| LM 5 | 4995 km2 |
| IL 5 | 531 km2 |
| IL 6 | 3417 km2 |
| Total | 10030 km2 |

Mwingi District is an Arid and Semi-Arid Lands (ASALs) area with bimodal type of rainfall.  Average rainfall ranges between 300 and 1000 mm per annum.

- Long Rains, March – May rainfall is unreliable

- Short Rains, October – December rainfall is the one farmers mostly rely on (see Annex C)

ii) Reasons/factors of land degradation in Mwingi

- Poor rainfall in terms of amounts, distribution

- High intensity rainfall that falls in thunderstorms destroying soils and vegetation

- Overstocking of livestock – major problem particularly around watering points.

- Poor farming practices – shifting cultivation

- Deforestation – charcoal burning, timber harvesting, herbalists harvesting medicinal plants, wood carvers

- High levels of poverty that encourages using environmentally unsustainable methods of livelihoods e.g.  charcoal burning

iii) Indicators of land degradation (see Figures in Annex D)

- presence of denuded areas

- presence of gullies

- low crop yields

- loss of biodiversity – extinction of certain species

- low water table

- siltation of dams

- poor livestock body conditions

IV. Coping strategies against land degradation

- Soil conservation measures – “fanya juu” etc.

- National Soil and Water Conservation Project

- Programmes such as Farmers’ Field Schools (FFSs), NALEP, SIDA, AAK, Catholic Diocese of Kitui World Vision, World Food Programme

- Water harvesting

- “Fanya”/Irrigation digits

- Water conservation

- Farming systems such manure application, fertilizer use, early maturing crops, early planting, drought resistant crops such as cow peas, pigeon peas, sorghum, millet, etc.

- Diversification of livelihoods e.g.  bee keeping, small businesses

v. Challenges

The following are among the challenges of resource degradation within Mwingi District.

- Increasing crop yields

- Incorporating suitable agro-forestry trees in the farming system

- Identifying road run-off points for water harvesting

- Preventing cultivation on hilly areas

- Identifying alternative livelihoods

- How to stop deforestation

Summary of Presentation by the District Environment Officer – National Environment Management Authority (NEMA)

NEMA coordinates environmental matters.  It does not implement any projects but works through other institutions.  Its key areas include:

- Public awareness

- Education on various environmental rules such as EMCA

- Environmental Impact Assessments

- Conservation measures using advocacy and people

Summary of Presentation by Mr.  Mwanga, the Deputy District Agricultural Officer (DDAO) on Farmers’ Field Schools (FFSs)

FFS is a new concept in Kenya and is one of the extension approaches.  It involves farmers in the extension work.  The concept was started in South East Asian countries as part of pest control measures using indigenous knowledge system.

In Kenya FFS programme was stared in Western as an Integrated Production and Pest Management (IPPM) in 1996.  In 2001 through funding by UNDP/FAO and GoK the IPPM was expanded to seven more districts including Mwingi.  Phase II of FFS programme started in Mwingi in 2004 through funding from FAO and The Netherlands Government that included Partnership Programme in Water Harvesting in three divisions of Mwingi.  The Government of Kenya has since expanded the programme to include the rest of the divisions.

Key area includes Participatory Extension Approach involving farmers in:

- Problem identification through ground work and public meetings

- Identification of enterprise areas

- Choice of place for regular meetings

- Encouraging growth  of indigenous crops

Lessons learnt through FFSs

- Empowerment in knowledge

- Leadership empowerment

- Initiation of innovative programmes

- Technology development

- High rates of technology adoption

- An entry point of new technologies

- Cost-effective means of spreading new ideas

- Enhancement of professionalism

- Development of strong farmer organizations e.g.  Mwingi District FFS Network

- Enhancement of Indigenous Knowledge Systems

Challenges

- Frequent crop failures hampering the learning process

- Low farmer participation

- Trials which address only a few problems leaving out a myriad other problems

- Low funding

- Low involvement of other departments due to lack or limited resources

- Limited staff trained in FFS methodology

Summary of presentations by representatives of FFSs participating in the workshop

There were two FFSs participating in the workshop.  These were Kalamba Muyo FFS from Mumoni Division and Kaghui FFS from Kyuso Division.

1.  Solomon Mutemi from Kalamba Muyo FFS

Kalamba Muyo FFS is three years old having started in 2003.  The FFS has 39 farmer members, 26 of which are women and 13 men.  They have a one acre field site that has been donated by the family of the FFS Chairlady.

i)  Key areas of focus

- Farming

- Water harvesting

- Learning through experiments at the field site

In learning and farming, they carry out trials with different crops.

In water harvesting they use tight contours and holes they dig in the farm.  The holes are also used for planting different plants as part of the trials.

ii) Challenges

- The area is dry and soil surface is hard and hence it is usually difficult to dig holes in the farm

- Frequent lack of food particularly during the period August – December.  They are trying out various crops to see which of the crops can carry them through this period.

- There is plenty of water that runs off during the rainy period hence efforts and technologies are needed to harvest the water.  Water harvesting will be one of the coping strategies.

- Resources are quite limited, particularly for water harvesting purposes.

- There is great need for water hence water provision using dams, wells, boreholes would be a very good way forward.

2.	Jacob Muli Mwova from Kaghui Farmers’ Field School

Kaghui FFS was started in 2001 with 32 members.  Currently the membership is 25 other members having left.  They went through training during the 2001 – 2002 period although learning still continues.  They have one farm that is used for income generating activities and a second farm they use for trials.  The farm they have is leased for a ten year period until the year 2010.  Since its inception Kaghui has created 6 other FFSs hence forming a zone.

Besides farming and trials, the FFS has goat rearing project.  When the FFS started it received a loan of Kenya Shillings 23,000/= from FAO through the Ministry of Agriculture.  Using the loan they bought 47 goats which were loaned to the members while the rest of the goats were managed by the group.  The members have since repaid the goats at   KSh.  100/- per oat.  They received additional assistance which they have used to buy 50 goats of which each member is going to be give 2 goats and each member will refund two female goats and Kenya Shillings 100/=.  The money raised will be used to start a cattle rearing programme while the goats will again be loaned to members.  Generally, the farmers’ income has significantly improved.

The farm is terraced to harvest water.  Future plans include using the farm for demonstration for others to learn and improving the goats through cross-breeding.

The major challenge is lack of water.  But the group reported that there is a seasonal river that passes nearby around which the water table is quite high at 28 – 40 feet deep.  If a borehole was sunk around the stream and installed with a pump, it may provide plenty of water that can be used for irrigation.  The Kaghui group is advocating for co-ownership and cost-sharing of all projects to ensure sustainability.

Other coping strategies in the area include formation of merry-go-rounds and practicing what they have learnt.

During brief discussions after the presentations it was reported that Muki, an NGO working in both Mumoni and Kyuso Divisions has carried out a Participatory Rural Appraisal (PRA) to seek a solution for the perpetual crop failures.  It was reported that water is the main problem of the area and a lot of earth dams were constructed but have since been filled up or silted

Session three - Discussions and Recommendations

The after of the 14th November was dedicated to questions and discussions.  The questions and discussions were centred on three areas – land degradation, early warning, and challenges.  To spearhead the discussion the following challenges were posed: After 40 years of independence Ukambani remains food insecure, what is it that can be done?  The Government of Kenya and several organizations, intergovernmental, non-governmental, and multi-nationals have implemented several projects in Ukambani, how come the problems are far from over?

The following is a summary of the discussions and outcomes from these discussions.  The opinions of the farmers in the these discussions were given the highest priority in each of the outcomes.

Major problems facing the farmers and pastoralists

- Frequent droughts

- Lack of  both domestic and irrigation water

- Famines

- High rates of poverty

- Diseases including HIV/AIDS and lack of medical facilities

- High rates of school drop-out

Challenges

- Provision of water

- Provision of medical facilities

- Insufficient extension services

- Limited initiative

- Limited resources

- Food insecurity

Actionable areas

- Environmentally friendly alternative livelihoods such as bee keeping

- Establishment of commercial woodlots as alternative livelihood

- Increased or enhanced water provision through harvesting facilities such as dams which may be used for water harvesting and fish farming.

- Conservation of water catchment areas

- Establishment of market groups for various products

- Establishment of tree nurseries

- Provision of water through boreholes and shallow wells

- Improvement of indigenous goat production through selection.

- Need for localized weather information

- Need for development of canals for water from River Tana for irrigation.

- Need for a full fledged weather station in the district.

- Value addition of existing agricultural and livestock products through processing.

- Promotion of traditional crops.

Barriers

- Lack of involvement of local stakeholders in the design and project development

- The local stakeholders have limited knowledge of the project objectives due to lack of sensitization.

- Negative Political interference among various local organizations and hence their objectives not always met.

Prioritization of the actionable areas

The actionable areas were prioritized in terms of those that should be given first preference.  It is emphasized here that the local stakeholders’ opinions, especially the farmers were given the most weight.

- Promotion of traditional crops (13)

- Provision of water through boreholes and shallow wells and increased or enhanced water provision through harvesting facilities such as dams which may be used for water harvesting and fish farming (7+3)

- Establishment of tree nurseries (6)

- Environmentally friendly alternative livelihoods such as bee keeping and the need for localized weather information (1+9)

- Establishment of market groups for various products (5)

- Improvement of indigenous goat production through selection (8)

- Value addition of existing agricultural and livestock products through processing

- Conservation of water catchment areas and establishment of commercial woodlots as alternative livelihood (4+2)

- Need for a full fledged weather station in the district

Specific activity areas that the project can address

- Promotion of indigenous crops

- Provision of water

  - Construction of earth dams

  - Construction of earth pans

  - Construction of shallow wells

  - Sand storage

  - Water harvesting

  - Construction of boreholes

- Establishment of tree nurseries

- Bee keeping

- Establishment of marketing groups e.g.  green-grams, sunflower, cotton

- Improvement of indigenous goats

- Conservation of catchment areas – gazettement of catchment areas

- Promotion of indigenous food crops such as millet, sorghum, cow peas, pigeon peas, etc.

# Annex 6: Maps

Figure 1.  Map of Kenya showing arid and semi-arid districts (ASALs)

Figure 2(a) and (b): Map of Mwingi District showing Administrative divisions and infrastructure (a) and Agro ecological zones (b)

(a)

(b)

# Annex 7: Photographs of UNDP pilot sites

Figure 3(a) and (b): Degraded land on a hill slope due to poor farming practices (a) and a degraded grazing land with a gully and exposed stones (b) due to high livestock populations within the UNDP pilot sites in Mwingi District

(a)

(b)

# SIGNATURE PAGE

Country: Kenya

UNDAF Outcome(s)/Indicator(s):

UNDAF Outcome 3.2: enhance Environmental Management for Economic Growth with Equitable Access to Energy Services and Response to Climate Change

Expected Outcome(s):

Enhanced capacity of regional, National, local level and community stakeholders to plan, manage and implement climate change adaptation measures

Expected Output(s):	Targeted knowledge-based tools developed for effective climate risk management; National and regional coordination and information sharing improved, for effective climate risk management; Advocacy and outreach programme prepared and conducted for replication of adaptation measures disseminated through national, regional and international networks; Community-level capacity increased to undertake adaptation measures as well as support Community based micro-projects.

Implementing partner: Office of the Prime Minister

Other Partners:	- Ministry of Agriculture

-Ministry of Livestock and Fisheries

- The World Bank

- IGAD

Total budget:		      	2,356,994

Allocated resources (GEF):      	1,000,000

- Other:

Office of Prime Minister	812,263

- In kind contributions

Government (Met. Dept):	244,681

Government (MOA):           	300,000

Programme Period: 2008-2012

Programme Component: _________

Project Title: Kenya: Adaptation to Climate Change in Arid and Semi-Arid Lands

Project ID: PIMS 3792; Atlas Project 00057371; Award 00047603

Business Unit: (KEN10)

Project Duration:	4 years

Management Arrangement: NEX

| On Behalf of | Signature | Date | Name/Title |
| --- | --- | --- | --- |
| Government Coordinating Authority |  |  | Dr Muusya Mwinzi, Director General National Environment Management Authority |
| Implementing Partner |  |  | Ms. Mary Ngari Permanent Secretary Office of the Prime Minister; Ministry of State for the Development of Northern Kenya and other Arid Lands |
| UNDP-Kenya |  |  | Mr. Aeneas Chuma Resident Representative, UNDP |

# Footnotes

Mwingi has recently been subdivided into two districts, Mwingi and Kyuso districts.  The project will cover activities in both districts.

GOK subdivided districts in 2007; however ALRMP operates within the original, larger administrative areas.  In this document, reference to districts refers to the original, longstanding districts of Kenya.

This will include complementing ongoing GEF funded initiatives such as the Agro-pastoralists Farmer Field School initiative (November 2006) that is also piloted in Mwingi and Kyuso Districts.