## Slide 1
Japan-Caribbean Climate Change Partnership
Project Monitoring, Evaluation and Reporting
Inception Workshop
27 January 2015
Barbados
United Nations Development Programme

## Slide 2
Everybody is involved!
Project Board
Beneficiary Representative
Beneficiary countries
CARICOM Secretariat
OECS Commission
Executive/Project Director
UNDP SRO, Barbados
UNDP RBLAC Regional Hub, Panama
Development Partners
Government of Japan
Project Organisation Structure
Project Assurance
UNDP SRO, Barbados
UNDP RBLAC Regional Hub, Panama
Project Management Unit (UNDP Barbados)
Project Manager
NAMA and NAP Technical Specialists
Communications Specialist
Project Associate
National Focal Points
Belize, Dominica, Grenada, Guyana, Jamaica, Saint Lucia, St Vincent and the Grenadines, Suriname
UNDP Country Offices
Belize, Barbados and the OECS, Guyana, Jamaica, Suriname
Technical Advisory Group
CCCCC
CIMH
CARPHA
CANARI
CARDI
UWI
CDEMA
UNFCCC RCC

## Slide 3: Adaptive Management
Assess problem
Design
Implement
Monitor
Evaluate
Adjust
Reducing uncertainty
Active learning
Informed decision-making
Formal, structured, systematic: not just trial and error
Notes: The systematic process for continually improving management policies and practices by learning from the outcomes of operational programmes
Monitoring & evaluation tools allow us to assess the success and results of projects, but – more importantly – to address problems as they arise by identifying and implementing changes that will improve and strengthen ongoing projects
Common scenarios:
Staff turnover
Non-delivery of contractors
Difficulties with collaborations
Natural disasters

## Slide 4: Adaptive Management Tools and approahces
Quarterly, Annual and Multi-year work plans and budget
Project Implementation Reports (annual, quarterly)
Field Visits, Consultations
Impact Assessments
Midterm Review (MTR) – Terminal Evaluation (TE)
Technical Reports
Results Framework / LogFrame

## Slide 5
Planning and Monitoring
Which result do I want to achieve? | In which units do I measure this result? | How much of these results units are available before the project is starting? | How many results units do I want to achieve, and by when? | How and where can I find data and info to verify that this result has been achieved? | Which risks could affect achievement of this result? Which conditions are necessary so that I have good chances of achieving this result? (conditions out of project influence)
Project Strategy / Output | Indicator | Baseline value | Target and benchmarks | Sources of verification | Risks and Assumptions
Project Results Framework – Project Document p 54

## Slide 6
Planning and Monitoring
Application Form for the Pilot Projects under Outcome 2

## Slide 7
Planning and Monitoring
Multi-Year Work-plan, Annual Work-plan

## Slide 8
Reporting
  Inception Report
  Quarterly Progress Reports
  Annual Project Report
  Technical Reports
  Project Publications
  Mid-term and final evaluation reports
  Audit Report

## Slide 9: Risk Management Why manage risk in a project?
projects are complex and therefore likely to face risks and challenges
Strengthen project and portfolio management (efficiency and effectiveness)

## Slide 10: Risk Management Seven Risk Categories
ENVIRONMENTAL
Natural disasters
Seasonal extremes
FINANCIAL
External: interest rates, exchange rate fluctuations, etc.
Internal: co-funding difficulties; financial mechanisms
OPERATIONAL
Complex design
Negligence/incompetence
Poor M&E; slow delivery
ORGANIZATIONAL
Institutional / implementation arrangements
Institutional / Execution capacity
POLITICAL
Government commitment; political will
Political instability; change in government
REGULATORY
New unexpected regulations, policies
Critical policy/legislation fail to pass
STRATEGIC
Partnerships failing to deliver
Mismatch between project scope/ambition and capacity

## Slide 11
# | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response
1 | Community not supportive of proposed interventions | December 2014 | Social/Political | Most of the interventions identified have not been validated with community level stakeholders. P = 2, I = 5 | UNDP has developed a visibility, communication and stakeholder engagement strategy which will ensure that all community based actions are implemented with the free, prior and informed consent of all stakeholders at community level.
2 | Slow financial delivery due to limited national absorption capacity | December 2014 | Financial | Slow financial delivery can result in disrupting the project’s timeframe and result in inability to achieve results on time P = 3, I = 4 | UNDP has decided to use the Direct Implementation Modality, which gives greater control for organisation or project outputs
3 | Natural hazard impact | December 2014 | Environmental | Hazard impact such as from a hurricane could severely delay project activities and result in inability to deliver project activities or even cause destruction to infrastructure. It would also divert national priorities and resources to response, recovery and reconstruction efforts. P = 5, I = 5 | In compliance with its corporate policy, the operation of PMU in Barbados will be covered by UNDP’s Barbados Business Continuity plan. This is also applicable to other project operations in other UNDP offices’. This would provide an opportunity for demonstrating the value of the project investment in execution of the capacities built; or through support from the wider region in applying such capacities to the affected country if not yet built locally.
4 | Change in Government | December 2014 | Political | Change in government can mean new priorities and, in some cases unwillingness to continue with development initiatives of a previous administration P = 3, I-5 | UNDP is undertaking wide consultations with national actors and ensuring alignment between project priorities and national development needs.

## Slide 12
M&E Work Plan and Budget
Project Document p69 M&E Work Plan and Budget
Multi-Year Work-Plan
4. 1 Inception/launch and Project Board Meetings | 4.1.1 Inception/launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNDP | GOJ | 61100 | Salary NP staff | 255,837.80 | 255,837.80
 | 4.1.2 Project Board Meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | Contractual Services - Individ | 41,371.26 | 41,371.26
 | 4.1.3 In-Country launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 72200 | Equipment and Furniture | 21,500.00 | 15,988.71
4.2 Project implementation and monitoring | 4.2.1 Quartery Progress Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 72400 | Communic & Audio Visual Equip | 8,300.00 | 34,655.99
 | 4.2.2 Annual Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71200 | International Consultants | 40,000.00 | 40,000.00
 | 4.2.3 Project Terminal Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 74100 | Professional Services | - | 20,000.00
 | 4.2.4 Monitoring Mission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71300 | Local Consultants | 25,531.25 | 25,531.25
 | 4.2.5 Mid-term Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 75700 | Training, Workshops and Confer | 36,351.79 | -
 | 4.2.6 Final Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71600 | Travel | 92,500.00 | 92,500.00
 | 4.2.7 Audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 74500 | Miscellaneous Expenses | 117,330.18 | 117,330.18