## Slide 1: 5.1: Gender-responsive monitoring and indicators
Gender in Adaptation Planning for the Agriculture Sectors Training workshop [Name of presenter] [Date]
Notes: Note to trainer: See Unit 5.1 in the Guide for Trainers for ideas on a session on measuring progress on adaptation from a gender perspective.

## Slide 2: Learning outcomes
Explain
Explain what issues are tracked as part of gender-responsive monitoring of adaptation.
Identify
Identify data sources for gender-responsive monitoring and key steps in measuring gender-related changes.
Design
Design gender-responsive indicators for monitoring gender in agricultural adaptation plans and projects.

## Slide 3: Part 1. Monitoring
The monitoring phase of adaptation planning involves tracking adaptation options, policies and plans to verify whether they are achieving desired targets.
An adaptation monitoring framework, also known as a results-based framework, defines in measurable terms the goal, outcomes, outputs, activities and inputs of a plan or policy.
Existing frameworks can be utilized and elaborated on for the purpose of monitoring adaptation-related issues in agriculture.

## Slide 4: Common terms used in monitoring
Goal/impact
Outcome
Output
Activities
Inputs
What will be achieved ultimately in agriculture with regards to adaptation?
Where will adaptation in agriculture be in five years?
What will adaptation programs or policies provide?
What will be done to produce outputs?
What financial, human and material resources are needed to implement activities?
Notes: Note to trainer: Before showing this slide, you may want to ask participants if they know the definitions of or can give examples of the key terms in a monitoring framework: goal, outcomes, outputs, activities and inputs. You can direct them to this table in the guide, Table 5.1.1.

## Slide 5: Adaptation monitoring framework
To track progress over time
Used for a variety of reasons
  enhancing learning on adaptation, including in the long term
  assessing effectiveness of what works and what doesn’t
  flexible management and adjustment of adaptation under climate uncertainty
  accountability to national decisionmakers and donors
  compliance with national and international reporting requirements, including UNFCCC

## Slide 6: Gender-responsive monitoring
An ongoing effort to assess impacts of a project or plan for women, men, girls and boys and the contribution of a project or plan to advancing gender equality and empowerment.
To carry out gender-responsive monitoring:
  develop gender-responsive indicators as part of the monitoring plan
  gather, record and validate information (including sex-disaggregated data)
  analyse the data with a focus on gender equality outcomes (How are men and women affected? Who benefits? Who influences decisions? Who uses and controls assets and resources?)
  communicate and use the information

## Slide 7: Why track gender as part of an adaptation monitoring framework?
Useful for
  exposing inequalities
  improving understanding of why changes happen for different groups
  tracking the performance of partners
  holding stakeholders accountable for meeting gender-related
When gender issues are monitored, including both the outcomes for different groups of people and changes at institutional level, it is possible to determine the extent to which a project or plan is contributing to transformative change and adjust if it is not meeting its targets.

## Slide 8: What gender issues of adaptation should be monitored?
When measuring the process of adaptation
Track advancement in implementing policies and plans with equitable participation and influence by women and men
When measuring adaptation outcomes
Track an increase in water availability for both men’s and women’s responsibilities during drought at sub-national level as a result of women and men employing labour-reducing adaptive practices like rain water harvesting.
When measuring an increase in adaptation capacity
Track % women, men who report increased access to financial resources and knowledge about climate change impacts, or report increased participation in farmers’ groups, or more sharing of decision-making at household level.
Notes: Note to trainer: Ask participants if they can think of other examples. See Box 5.1.1 for further ideas.

## Slide 9: Key considerations for carrying out gender-responsive monitoring
Beneficiaries have a role to play in setting baselines and collecting data
Commitment needed from numerous actors to contribute data and analysis
Competencies may need to be strengthened
Notes: Note to trainer: See Box 5.1.2 for more detail

## Slide 10: Part 2. Indicators
An indicator is a measurable variable that helps assess the current situation and track change over a period of time.
Gender indicators (GIs) (also referred to as gender-sensitive indicators or gender-responsive indicators)
  measure gender-related changes over time
  expressed as a measurement, number, opinion or perception based on quantitative or qualitative data
  express outcomes for different groups or progress toward gender equality against a baseline
  developed through an inclusive process

## Slide 11: Types of indicators
Quantitative indicators
based on quantifiable data, often collected through a survey, and are usually expressed as numbers or percentages
Qualitative indicators
measure quality of perceptions and experiences, as well as behaviour and attitudes, and are based on data collected through participatory methods
e.g. number/percentage of farmers adopting climate-resilient livestock practices by age and sex, or the percentage of female adaptation committee members
e.g. growth in knowledge and skills on climate change in the sector, by sex

## Slide 12: Formulating gender indicators
Are the objectives of the plan or project gender-responsive?
Do the proposed activities address the needs and priorities of both women and men and address the gender issues that have been identified in a gender analysis?
Is there sex-disaggregated data to use in relation to the goals?
Which indicators will tell us whether we have undertaken the activity or reached the objective? Are they written to guarantee that data will be disaggregated by sex (and other relevant socioeconomic variables)? What is the target and time frame?
Is the additional data needed to track the indicators easy to collect, use and understand?
Adapted from Murray (2019b)

## Slide 13: Example
Goal/impact
Outcome
Output
Policies recognize women and men as key actors in adaptation and enable them to benefit equally.
Impact assessments of possible gender-differentiated outcomes of policy options are undertaken.
Resilience of rural women and men to the impacts of adaptation on agricultural livelihoods is improved.
Indicator: Number of gender-responsive targets included in the policy.
Indicator: Percentage of impact assessments that include gender analysis